## AP 2023
PLANIFICACIÓN DE ACTIVIDADES / ANNUAL PLAN REV 00 FECHA DE EMISIÓN 17/10/17
FECHA DE REVISIÓN 17/10/17
Nombre del Programa / Programme: Liderando desde el Sur / Leading from the South
Periodo de ejecución/Execution period: 2023
Donante/ Donor: MFA - Netherlands
Coordinadora/Programme Coordinator: Natalia Eberbach
OUTCOMES | OUTPUTS | ACTIVITY # | CORE ACTIVITIES | INTENDED RESULTS | HUMAN RESOURCES INVOLVED | TIMEFRAME (Year 2023)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Outcome 1 (ultimate): Improved pre-conditions leading to an enabling environment for women’s rights and gender equality. | Output 1. Strengthened organisations and activists´ active participation in key spaces to advocate for transformational change. | 1 | Special programme to promote grantees participation in regional/international conferences/forums | At least 7 key participations promoted | PC, PA, AO, MELO
|  | 2 | Grantees training programme (meetings/workshops) | At least 3 training sessions developed | PC, PA, AO, MELO, EC
Outcome 2. Strengthened ability of SWROs, networks and alliances to lead change and transform societies towards the full achievement of gender equality and human rights in LAC. | Output 2. Strengthened political capacities of SWROs and groups to lead change, advocate for gender equality and human rights and to hold stakeholders accountable. | 3 | Special Support Grants to promote movement- building | At least 3 SSG delivered | PC, PA, AO, MELO, EC
| Output 3. Increased linkages with local, national, subregional and regional peer organisations, boosting organisational learning processes, strengthening L&A strategies and encouraging joint initiatives. | 4 | Anual L&L meetings among LFS grantees | At least 3 meetings conducted | ED, PC, PA, AO, MELO, EC
|  | 5 | LFS first inter-regional thematic convening for grantees from the 4 WF partners of the LDS consortium | One inter-regional thematic convening held in Asia, in which FMS grantees participated | PC, AO, MELO
|  | 6 | Special programme to promote exchanges among grantees | At least 5 exchanges promoted | PC, PA, AO, MELO
|  | 7 | Annual Face to Face meeting among LAC Women's Funds | At least one face o face meeting among LAC WFs conducted | ED, PC, MELO, AO
Outcome 3. Improved sustainability of SWROs, so their agendas, demands and visions are recognised and sustained by society. |  | 8 | Anual L&L meeting among LFS Consortium | Participation in one face to face meeting | PC, PA, AO, MELO
| Output 4. Strengthened institutional capacities of SWROs and groups to sustain their structures. | 9 | Project renewal process for 41 grassroots organisations | Renewals processed | ED, PC, AO, MELO
|  | 10 | Launching of a regional Call for Proposals for renewing large and midsized grantees. | Call launched | ED, PC, AO, MELO
|  | 11 | Official communication of renewed projects | Grantees officially informed | PC, CO
|  | 12 | Signature of Cooperation Agreements | Cooperation Agreements signed | PC, PA, AO
|  | 13 | Grant delivery process to grassroots organisations (41), midsize and large organisations (Call 2021+Call 2023) and the 6 local partners (LAC Women Funds) | Disbursements executed | PC; AO
|  | 14 | Virtual meetings with grantees | At least 24 virtual meetings conducted | PC, PA, AO, MELO, CO
|  | 15 | Field visitis to grantees | At least 8 field visits conducted | PC, CO, MELO
|  | 16 | Gathering, analyzing and systematizing narrative and financial reports of the grantees | Evaluation conducted | ED, PC, AO, MELO
Outcome 4. Strengthened involvement of women and LBTIQ+ people in policy and decision-making processes at all levels, including in context of conflict and peace building and gender-sensitive responses to health/social crisis. | Output 5. Strengthened knowledge on women, girls and LBTIQ+ people human rights with a focus on SGBV, political leadership and participation, economic justice, and environmental justice and climate change, reinforcing both organisational and individual learning and L&A processes. | 17 | Call for proposals for the MTR (elaboration and dissemination of ToR, selection of a consultant team and beggining of the consultancy process) and management of the MTR process. | MTR finalized | ED, PC, AO, MELO
|  | 18 | Submision of the requested data to the MTR team of the MFA for the realization of this joint, independant an external review financed and conducted by the MFA. | Information sumitted | ED, PC, AO, MELO
|  | 19 | Elaboration of a joint MEL report among the LFS Consortium members. | Joint MEL report produced. | ED, PC, MELO
|  | 20 | Dissemination of relevant information and communication | At least 12 communication actions implemented | PC, CO
|  | SUPPORT ACTIVITIES |  | INTENDED RESULTS | HUMAN RESOURCES INVOLVED | TIMEFRAME (Year 2023) 1: TIMEFRAME (Year 2022)
|  | 21 | Collective elaboration of the annual narrative progress report for the MFA | Narrative report to the MFA elaborated | MELO; PC
|  | 22 | Collective elaboration of the annual financial progress report for the MFA | Financial report to the MFA elaborated | AO, PC
|  | 23 | Supervision of the of annual audit opinion and audit report elaboration process | Annual audit opinion and audit report supervised | ED, PC
|  | 24 | Preparation of short videos (Voices from the ground) | At least 2 "Voices from the ground" videos elaborated | CO, MELO
|  | 25 | Elaboration of LDS in LAC strategic document | LDS in LAC strategic document elaborated | PC, MELO, EC
|  | 26 | Production of comms products (audiovisual materials, social media, publications, etc) | At least 2 comms products elaborated | CO
|  | 27 | Coordination among the 4 Comms Officers of the WFs partners for joint activities | At least 4 working groups meetings conducted | CO
|  | 28 | Coordination among the 4 MEL Officers of the WFs partners for joint activities | At least 4 working groups meetings conducted | MELO
|  | 29 | Coordination among the 4 Finances Officers of the WFs partners for joint activities | At least 4 working groups meetings conducted | AO
|  | 30 | Coordination among the 4 Programme Coordinators Officers of the WFs partners for joint activities | At least 4 working groups meetings conducted | PC
|  | 31 | Coordination among the 6 LAC Women's Funds partners | At least 3 meetings conducted | ED, PC
|  | 32 | Exchanges among WFs members | At least 1 exchange amomg WFs members executed | PC, AO, CO, MELO
|  | 33 | Participation in regional/international conferences/forums/meetings | FMS participation in at least 4 regional/international conferences/forums/meetings | ED, PC
|  | 34 | Participation in strategic discussions/ policy dialogues organised by the MFA | Representatives of the the LFS consortium participation in the 2 strategic discussions/ policy dialogues organised by the MFA | ED, PC
|  | 35 | Joint and individual regular checkins among WFs and MFA | At least 2 virtual meetings amomg WFs and the MFA | ED, PC, AO, CO, MELO
|  | 36 | Permanent communication among partner WFs at all levels | At least 3 virtual meetings per year | ED, PC, AO, CO, MELO
|  | 37 | Development of joint advocacy actions among the four WFs to advance key issues and give visibility to the LFS model | At least 2 joint advocacy actions among the four WFs to advance key issues and give visibility to the LFS model per year | ED, PC, MELO
|  | 38 | Systematization and documentation of the programme stages | At least one learning product elaborated | PC, CO, MELO, GD, EC
|  | 39 | Internal staff trainings and coordination meetings | At least 4 staff trainings/coordination meetings conducted | ED, PC, AO, CO, MELO
|  | 40 | Technical assitance to grantees to fulfill reports | Grantees assisted | MELO, AO
|  | 41 | Revision/follow up of narrative and financial mid-term reports sent by the coparts | 100% of the submitted reports reviewed | PC, MELO, AO
|  | 42 | Annual audit of the quality management system (ISO 9001 certification) | Annual Annual audit of the quality management system conducted | ED, PC, PA, AO, MELO
References:
ED: Executive Director
PC: Programme Coordinator
PA: Programme Assistant
MELO:Monitoring, Evaluation and Learning Officer
AO: Administrative Officer
CO: Communication Officer
GD: Graphic Designer
EC: External Consultant