## Guidance
GLOBAL POVERTY ACTION FUND (GPAF) LOGICAL FRAMEWORK TEMPLATE WITH ACTIVITY LOG A logical framework or logframe is required for all GPAF projects. COMMUNITY PARTNERSHIP WINDOW Applicants must fully complete both the logical framework and activities log tabs of the logframe template and submit together with their proposal. For guidance on logical frameworks please refer to the How To Note. IMPORTANT INFORMATION ON COMPLETING THE LOGFRAME • Each logframe must be saved as a separate file in Excel format (*.xls) • The logframe must not include any more than 6 (six) outputs • The logframe must not exceed a total of 155 spreadsheet lines • The font should be no smaller than Arial 9 when completed Logframes which do not conform to the above criteria will not be considered.

## Logical Framework
ORGANISATION NAME | Carers Worldwide
PROJECT NAME | Improving the physical and mental health, promoting social inclusion and increasing the household income of 1,500 carers of mentally ill individuals in Nepal
GPAF ref. No.
IMPACT | Impact Indicator 1 |  | Baseline | 2015-03-01 | 2016-03-01 | Target (June 2017)
Improved physical, emotional, economic and social wellbeing among carers of people with mental illness and epilepsy in Baglung and Myagdi districts of Nepal | Percentage of people living below poverty line in Baglung and Myagdi districts of Nepal | Planned | Baglung 25.03% Myagdi 33.89% |  |  | 21% (target set by Government of Nepal in 2013)
Achieved
Source
Nepal Poverty Map 2011, World Bank and Central Bureau of Statistics, Nepal
| Impact Indicator 2 |  | Baseline | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Provision made by district level government for carers of people with mental illness and epilepsy | Planned | No provision at district level for carers of people with mental illness and epilepsy |  | 3 VDCs in Baglung and Myagdi provide financial and material support to carers | 6 VDCs in Baglung and Myagdi provide financial and material support to Carers associations
Achieved
Source
Village Development Committee records, carers group meeting minutes, LEADS field visit reports
| Impact Indicator 3 |  | Baseline | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Government Poverty Reduction Strategy Paper (PRSP) includes mention of carers and specific measures of their social and economic wellbeing | Planned | PRSP does not include carers of PWMIE |  |  | Latest PRSP includes carers as a vulnerable target group
Achieved
Source
Poverty Reduction Strategy Paper of Nepal Government
OUTCOME | Outcome Indicator 1 |  | Baseline Sept-14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumptions
Carers of PWMIE, their households and PWMIE in Baglung and Myagdi districts have increased income and social inclusion and improved access to medical and education services | Number and percentage of a) carers (M/F/C) b) carer households c) carer household members with average incomes above Nepal poverty line (NPR95 per day = £0.60 = $1) based on average household size of 5 = total of 7,500 household members | Planned | a) 3% (9) b) 3% (9) c) 3% (45) | a) 20% (300) (M: 105; F: 150; C: 45) b) 20% (300) c) 20% (1500) | a) 50% (750) (M:255; F: 370; C: 125) b) 50% (750) c) 50% (3750) | a) 85% (1275) (M: 435; F: 650; C: 190) b) 85% (1275) c) 85% (6375) | (i) Stigma and exclusion in the community are overcome and carers are able to participate fully in project activities. (ii) Specific difficulties and stigma related to vulnerable groups such as women and Dalits/tribals will be addressed and overcome so that they will be able to participate fully in the project. (iii) FCHVs (grassroots level health education volunteers working in the villages, appointed and trained by the government through the Village Development Committees) will remain available and committed to the project and will prove capable of taking on the new tasks assigned to them. (iv) Local government authorities will engage in and co-operate with the project, its staff and its activities. (v) Nepal will remain politically stable.
Achieved
Source
|  |  | Baseline data from survey conducted by LEADS and Carers Worldwide Sept 2013, sample size: 300 carers (M:39%; F:61%) |  | Milestones and targets data from LEADS annual progress reports and carer surveys conducted annually by LEADS staff via carers groups and home visits
| Outcome Indicator 2 |  | Baseline Sept-14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| a) Number of agreements signed with Village Development Committees to provide individual child carer clubs with the financial resources to buy stationary b) Number of carers groups signing MoUs with Village Development Committees for the resources to establish revolving funds for the groups | Planned | a) 0 b) 0 | a) 3 b) 5 | a) 8 b) 15 | a) 15 b) 30
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes, records of Village Development Committees
| Outcome Indicator 3 |  | Baseline Sept-14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number and percentage of carers who have regular access to services (counselling and health) and as a result do not experience significant a) physical or b) mental health difficulties | Planned | a) 31% (93) b) 23% (69) | a) 45% (675) b) 45% (675) (figures to be disaggregated by male/female/child by 30/04/2015) | a) 60% (900) b) 60% (900) (figures to be disaggregated by male/female/child by 30/04/2015) | a) 75% (1125) b) 75% (1125) (figures to be disaggregated by male/female/child by 30/04/2015)
Achieved
Source
Baseline data from survey conducted by LEADS and Carers Worldwide Sept 2013, sample size: 300 carers (M:39%; F:61%); Milestones and targets data from LEADS annual progress reports and carer perception surveys conducted annually by LEADS staff via carers groups and home visits
| Outcome Indicator 4 |  | Baseline Sept -14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Carers are better able to express their positions in interactions with local government authorities and in other forums | Planned | Carers currently have no voice | 5% (75) of carers feel more confident to express their opinions (figures to be disaggregated by male/female by 30/04/2015) | 20% (300) of carers feel more confident to express their opinions (figures to be disaggregated by male/female by 30/04/2015) | 50% (750) of carers feel more confident to express their opinions (figures to be disaggregated by male/female by 30/04/2015)
Achieved
Source
Baseline data from survey conducted by LEADS and Carers Worldwide Sept 2013, sample size: 300 carers (M:39%; F:61%); Milestones and targets data from carer perception surveys conducted annually by LEADS staff via carers groups and home visits
| Outcome Indicator 5 |  | Baseline Jul -14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number and percentage of carers regularly accessing respite care when required | Planned | There are no structured respite care services available to carers | 10% (150) (figures to be disaggregated by male/female/child by 30/04/2015) | 25% (375) (figures to be disaggregated by male/female/child by 30/04/2015) | 60% (900) (figures to be disaggregated by male/female/child by 30/04/2015)
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes, reports and data submitted by community caring centre staff/volunteers
| Outcome Indicator 6 |  | Baseline Sept-14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of target child carers attending school | Planned | 0 | 50 (to be disaggregated by male/female by 30/04/2015) | 150 (to be disaggregated by male/female by 30/04/2015) | 225 (to be disaggregated by male/female by 30/04/2015)
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes, reports and data submitted by school staff
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
220308
INPUTS (HR) | DFID (FTEs)
11.95 +300 FCHVs
OUTPUT 1 | Output Indicator 1.1 |  | Baseline Jul -14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumption
Strengthened medical and counselling facilities for carers | Number of government health workers a) trained in carer needs and b) demonstrating good practice by asking carers about their needs during consultations and helping them to address their needs where necessary | Planned | 0 | a) 20 (M: 15; F: 5) b) 20 (M: 15; F: 5) | a) 70 (M: 50; F:20) b) 70 (M: 50; F:20) | a) 120 (M: 85; F: 35) b) 120 (M: 85; F: 35) | (i) Health workers will engage in the process positively. (ii) Local government authorities will engage in and co-operate with the health related activities. (iii) The FCHVs will remain available and committed to the project and will prove capable of learning new skills and carrying out their counselling role effectively.
Achieved
Source
Home visit reports, field visit reports, training events, quarterly and annual progress reports, carers group meeting minutes, carer perception surveys in which carers will be asked whether health workers have at any time i) asked them about their needs and ii) helped them to address their needs where necessary
| Output Indicator 1.2 |  | Baseline Jul -14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| a) Number of FCHVs trained as barefoot counsellors for carers b) able to highlight 2 key training messages and c) number of carers covered by the counselling service | Planned | 0 | a) 50 b) 30 c) 60 (M:10; F:35; B:8; G:7) | a) 175 b) 105 c) 360 (M:110; F:185; B:35; G:30) | a)300 b) 195 c) 1060 (M:360; F:535; B:85; G:80)
Achieved
Source
Home visit reports, field visit reports, training events, quarterly and annual progress reports, carers group meeting minutes
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline Jul -14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
10% | Numbers of a) carers and b) family members assisted by an FCHV to access health services in the last 6 months | Planned | 0 | a) 50 (M:10; F:20; B:10; G:10 b) 250 (M:50; F:100; C:100) | a) 300 (M:60; F:120; B:65; G:55 b) 1500 (M:300; F:600; C:600) | a) 1000 (M:260; F: 470; B:140; G:130) b)5000 (M:1300; F:2350; C:1350)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Home visit reports, field visit reports, quarterly and annual progress reports, carers group meeting minutes; carer perception surveys; sources will document ways FCHV assist eg. accompanying person to the medical centre, arranging alternative care to enable carer to access healthcare, talking to other family members about the need to seek healthcare, liaising with healthcare professional on person's behalf, collecting medicines |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 12039 |  | 0 | 0 | tbc | 100%
INPUTS (HR) | DFID (FTEs)
9 + 300 FCHVs
OUTPUT 2 | Output Indicator 2.1 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumptions
60 carers mutual support groups are formed and operational | Number of a) groups formed and b) carers who are members of groups | Planned | 0 | a) 15 b) 300 (figures to be disaggregated by male/female by 30/04/2015) | a) 45 b) 900 (figures to be disaggregated by male/female by 30/04/2015) | a) 60 b) 1200 (figures to be disaggregated by male/female by 30/04/2015) | (i) Carers have trust in project staff and overcome their isolation to participate in group activities. (ii) Carers will come together and be prepared to work effectively as groups to achieve their ends, without issues of discrimination (for example, against women or Dalit/tribal individuals) hindering the process. (iii) There is the interest and political will amongst district officials to recognise and include specific provision for carers into their programmes.
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes
| Output Indicator 2.2 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of FCHVs trained to facilitate the groups | Planned | 0 | 75 | 225 | 300
Achieved
Source
Field visit reports, quarterly and annual progress reports, training records
| Output Indicator 2.3 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of group meetings held (24 meetings per group per year) | Planned | 0 | 180 per year | 1080 per year | 1440 per year
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes
| Output Indicator 2.4 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of rechargable mobile phone cards issued to enable carers to stay in contact for mutual support and to access necessary medical support | Planned | 0 | 60 | 540 | 720
| (1 phone card is issued to each carers group as they are formed and topped up monthly with sufficient credit to allow an appropriate amount of calls) | Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
20% | Number of Carers Associations formed and registered | Planned | 0 | 0 | 1 | 2
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers association meeting minutes, training events, records of the Social Welfare Council in Kathmandu
| Output Indicator 2.6 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of Carers Association members trained in social, economic and inclusion rights of carers | Planned | 0 | 0 | 11 (M:4; F:7) | 22 (M:8; F:14)
|  | Source |  |  |  |  | RISK RATING
|  | Carers group and carers association meeting minutes, quarterly and annual progress reports, training records |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 20979 |  | 0 | 0 | tbc | 100%
INPUTS (HR) | DFID (FTEs)
10.45 + 300 FCHVs
OUTPUT 3 | Output Indicator 3.1 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumption
Alternative care and respite arrangements for carers are set up and working | Number of volunteers trained to run and staff community caring centres | Planned | 0 | 0 | 30 (all female) | 50 (all female) | (i) Local authorities/communities provide the suitable physical space needed for the centres. (ii) Suitable volunteers are identified and issues of prejudice against PWMIE do not hinder the process. (iii) Individual PWMIEs remain stable enough to enable them to access the centres safely.
Source
Carers group and carers association meeting minutes, quarterly and annual progress reports, training records
| Output Indicator 3.2 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of community caring centres a) established and b) open at least 3 days per week | Planned | 0 | 0 | a) 30 b) 30 | a) 50 b) 50
|  | Source |  |  |  |  | RISK RATING
|  | Carers group meeting minutes, quarterly and annual progress reports, community caring group documentation |  |  |  |  | Low
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
15% | Number of carers (M/F) who a) have heard of the local community caring centre; b) intend to use it; c) have used it already | Planned | 0 | 0 | a) 900 (M:350; F:550) b) 740 (M:290; F:450) c) 150 (M:50; F:100) | a) 1200 (M:468; F:732) b) 960 (M: 375; F:585) c) 350 (M:150; F:200)
|  | Source |  |  |  |  | RISK RATING
|  | Carers group meeting minutes, quarterly and annual progress reports, community caring group documentation |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 6762 |  | 0 | 0 | tbc | 100%
INPUTS (HR) | DFID (FTEs)
8.6FTEs + 300 FCHVs
OUTPUT 4 | Output Indicator 4.1 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumption
Carers have access to livelihoods and skills training opportunities | Number of a) livelihoods/skills trainings offered and b) number of attendees | Planned | 0 | a) 4 b) 100 (M:40; F:60) | a) 10 b) 595 (M: 245; F:350) | a) 10 b) 1050 (M:420;F:630) | (i) Carers are given access to government and NGO livelihoods and training schemes. (ii) The process of selection for loans is not hindered by issues of stigma or discrimination (for example, against women or Dalits/tribals)
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes showing discussions regarding livelihoods opportunities and benefits, government department documentation and NGO training institute documentation regarding attendance
| Output Indicator 4.2 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of carers trained in marketing and other skills required to pursue their livelihood activities successfully | Planned | 0 | 20 (M:5; F:15) | 70 (M:25; F:45) | 120 (M:45; F:75)
Achieved
Source
Field visit reports, quarterly and annual progress reports, carers group meeting minutes recording progress with chosen livelihoods, training records maintained by LEADS staff
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
30% | Number of loans applied for by carers to enable initiation of livelihoods activities | Planned | 0 | 0 | 135 | 320
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Field visit reports, quarterly and annual progress reports, carers group meeting minutes recording discussions regarding loans, LEADS documentation regarding loans applied for and given |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 38807 |  | 0 | 0 | tbc | 100%
INPUTS (HR) | DFID (FTEs)
9.85 FTEs + 300 FCHVs
OUTPUT 5 | Output Indicator 5.1 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumptions
Support in place to enable child carers to attend school regularly | Number of FCHVs trained on the specific needs of child carers | Planned | 0 | 75 | 175 | 300 | (i) Local government authorities will engage in and co-operate with the education related activities. (ii) The FCHVs will remain available and committed to the project and will prove capable of learning new skills and carrying out their role with child carers effectively. (iii) School teachers will engage in the process positively. (iv) School teachers, once trained, will remain in post. (v) School authorities will provide the space required for the child carer clubs
Achieved
Source
Field visit reports, quarterly and annual progress reports, training records
| Output Indicator 5.2 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of teachers trained on the specific needs of child carers |  | 0 | 50 (M:30; F:20) | 100 (M:60; F:40) | 150 (M:90; F:60)
Achieved
Source
Field visit reports, quarterly and annual progress reports, training records
| Output Indicator 5.3 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of a) child carer clubs established, b) child carers (M/F) intending to use a club and c) child carers (M/F) who have used a club already |  | 0 | a) 10 b) 75 (M:40; F:35) c) 50 (M:26; F:24) | a) 25 b) 175 (M:90; F:85) c) 125 (M:66; F:59) | a) 45 b) 225 (M:119; F:106) c) 225 (M:119; F:106)
Achieved
Source
Field visit reports, quarterly and annual progress reports
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
10% | Number of child carers provided with education materials |  | 0 | 25 (M-15/F-10) | 75 (M-50/F-25) Total: 100 (M-65/F-35) | 50 (M-30/F-20) Total: 150 (M-95/F-55)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Field visit reports, quarterly and annual progress reports |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 9992 |  | 0 | 0 | tbc | 100%
INPUTS (HR) | DFID (FTEs)
8.6 FTEs + 300FCHVs
OUTPUT 6 | Output Indicator 6.1 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017) | Assumptions
Capacity strengthened to promote needs of carers and advocate for policy change | Number of a) human rights and inclusion training programmes conducted and number of attendees: b) LEADS staff, c) carers, d) volunteers and e) professionals | Planned | 0 | a) 17 b) 13 (M:2; F:11) c) 0 d) 200 (all female) e) 70 (M:45; F:25) | a) 45 b) 13 (M:2; F:11) (not cumulative as same people) c) 11 (M:4; F:7) d) 300 (all female) (not cumulative as some people the same) e) 170 (M:110; F:60) | a) 72 b) 13 (M:2; F:11) (not cumulative as same people) c) 22 (M:8; F:14) d) 300 (all female) (not cumulative as some people the same) e) 270 (M:175; F:95) | (i) LEADS staff, volunteers and professionals will engage effectively in the training processes and remain in post. (ii) Local government authorities will co-operate with the training activities and release staff to attend. (iii) Training programmes will be able to run as planned and not be adversely affected by weather, local/national events or political instability. (iv) National Disability Network members will co-operate and engage in the process of discussing and addressing the issue of carers.
Achieved
Source
Quarterly and annual progress reports, training records
| Output Indicator 6.2 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Number of biennial information and advocacy seminars organised by carers and LEADS staff for district authorities | Planned | 0 | 0 | 2 | 4
Achieved
Source
Quarterly and annual progress reports
| Output Indicator 6.3 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
| Needs and rights of carers becomes a standing agenda item at meetings of the National Disability Network | Planned | Carers do not feature as an issue | One off presentation to Network members regarding carers work | Representatives from Carers Associations attend a meeting and raise awareness around their needs and rights | Topics related to carers are discussed at every meeting
Achieved
Source
LEADS progress reports, minutes of National Disability Network
IMPACT WEIGHTING (%) | Output Indicator 6.4 |  | Baseline Jul - 14 | 2015-03-01 | 2016-03-01 | Target (June 2017)
15% | Number of requests made by carers groups to VDCs for resource allocation to support carer needs | Planned | 0 | 3 | 5 | 10
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Carers group meeting minutes, copies of request letters |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
12855
INPUTS (HR) | DFID (FTEs)
11.95 FTEs

## Activities Log
OUTPUT 1 | ACTIVITY 1.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Strengthened medical and counselling facilities for carers | 120 Health workers from 60 government health institutions (sub health post and health posts at village level) will be trained to understand needs and constraints on carers | 20 | 70 | 120 | Health workers and local government authorities do not engage in the process; trained health workers transfer to another district; FCHVs do not commit to the project and/or are not able to learn the new skills required. | District Coordinators
| ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| a) 300 FCHVs trained as barefoot counsellors; b) 195 FCHVs able to highlight 2 key training messages; c) 1060 carers covered by the counselling service | a) 50 b) 30 c) 60 | a) 175 b) 105 c) 360 | a) 300 b) 195 c) 1060 |  | District Coordinators
| ACTIVITY 1.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| a) 1000 carers and b) 5000 family members assisted by an FCHV to access health services | a) 50 b) 250 | a) 300 b) 1500 | a) 1000 b) 5000 |  | District Coordinators and CBSMs
OUTPUT 2 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Formation of 60 carers’ mutual support groups, providing emotional support to reduce isolation, improve wellbeing and capacity to care and providing a platform to advocate for the rights of carers at a local, regional and national level, leading to changes in policy and practice | Formation of 60 carers groups across 60 Village Development Committees in 2 districts to include 1200 carers; and being regularly attended by 1200 carers | 15 groups 300 carers | 45 groups 900 carers | 60 groups 1200 carers | High level of hesitation of carers to come into a group; issues of discrimination (for example, against women or Dalit/tribal individuals) hinder the group process; district officials do not have the interest or political will to recognise and include specific provision for carers into their programmes; misuse of phones; carers lack confidence to participate at association level | District coordinators
| ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| 300 FCHVs trained to facilitate carers groups | 75 | 225 | 300 |  | Livelihood Coordinator
| ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Carers group meetings held regularly, facilitated by 300 FCHVs | 180 meetings held | 1080 meetings held | 1440 meetings held |  | CBSMs
| ACTIVITY 2.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Rechargable mobile phone cards issued to enable carers to stay in contact for mutual support and to access necessary medical support (1 phone card issued to each carers group as they are formed and topped up monthly with sufficient credit to allow an appropriate amount of calls) | 60 | 540 | 720 |  | Finance Officer/District Coordinator
| ACTIVITY 2.5 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| One Carers Association (CA) formed in each district and registered with the Chief District Officer and the Social Welfare Council in Kathmandu; |  | 1 Carers Association formed and registered | 1 Carers Association formed and registered |  | Executive Director/Project Director
| ACTIVITY 2.6 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| 11 members in each Carers Association trained on the social, economic and inclusion rights of carers |  | 11 carers trained | 22 carers trained |  | Executive Director/Project Director/Livelihood Coordinator
| ACTIVITY 2.7 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Quarterly meetings of each Carers Association held |  | 4 meetings of 1st CA held | 8 meetings held - 4 for each CA |  | District Coordinators/ CBSMs
| ACTIVITY 2.8 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Annual Carers Day held each year in the first 2 years, followed by a Carers Week in the 3rd year with the aim of creating awareness of the needs and rights of carers and achieving recognition and subsequent policy changes for carers | 1 Carers Day held across both districts | 1 Carers Day held across both districts | Carers Week celebrated across both districts |  | Executive Director/Project Director
OUTPUT 3 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Alternative care and respite arrangements for carers are set up and working | Volunteers trained to run and staff community caring centres |  | 30 | 50 | Volunteers do not come forward to support the centres; Physical spaces are not provided by authorities/ community; PWMIE are not stable enough to use the centres | District coordinators
| ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Community caring centres established and running |  | 30 | 50 |  | District coordinators
| ACTIVITY 3.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Carers a) informed about ; b) making plans to use; c) actually using community caring centres |  | a) 900 b) 740 c) 150 | a) 1200 b) 960 c)350 |  | District coordinators
OUTPUT 4 | ACTIVITY 4.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Carers have access to livelihoods and skills training opportunities | a) livelihoods/skills trainings offered and b) carers attending the training | a) 4 b) 100 | a) 10 b) 595 | a) 10 b) 1050 | Carers are not given access to government and NGO livelihoods and training schemes; the process of selection for loans is hindered by issues of stigma or discrimination (for example, against women or Dalits/tribals) | Executive Director/Project Director/Livelihood Coordinator
| ACTIVITY 4.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Carers trained in marketing and other skills required to pursue their livelihood activities successfully | 20 | 70 | 120 |  | Executive Director/Project Director/Livelihood Coordinator
| ACTIVITY 4.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Loan application process established via carers groups and carers supported to apply for loans to enable initiation of livelihoods activities |  | 135 | 320 |  | Project Director/Livelihood Coordinator/District Coordinators
OUTPUT 5 | ACTIVITY 5.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Support in place to enable child carers to attend school regularly | 300 FCHVs trained to address the specific needs of child carers and their school attendance | 75 | 175 | 300 | Local government authorities do not co-operate with education related activities; FCHVs do not commit to the project and/or are not able to learn the new skills required; school teachers do not engage in the process positively; trained school teachers are transferred; school authorities do not provide the space required for child carer clubs | District Coordinators
| ACTIVITY 5.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| 150 school teachers sensitised to the needs of child carers | 50 | 100 | 150 |  | District Coordinators
| ACTIVITY 5.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| a) child carer clubs established and b) child carers supported to attend the clubs | a) 10 b) 50 | a) 25 b) 125 | a) 45 b) 225 |  | District coordinators/ CBSMs
| ACTIVITY 5.4 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| 150 child carers provided with school materials | 25 children provided with materials | 75 children provided with materials | 50 children provided with materials |  | District coordinators/ CBSMs
OUTPUT 6 | ACTIVITY 6.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Capacity strengthened to promote needs of carers and advocate for policy change | a) human rights and inclusion training programmes conducted and attended by: b) LEADS staff, c) carers, d) volunteers and e) professionals | a) 17 b) 13 c) 0 d) 200 e) 70 | a) 45 b) 13 (not cumulative as same people) c) 11 d) 300 (not cumulative as some people the same) e) 170 | a) 72 b) 13 (not cumulative as same people) c) 22 d) 300 (not cumulative as some people the same) e) 270 | LEADS staff, volunteers or professionals do not engage effectively in the training processes and/or leave their posts; local government authorities do not release staff to attend training or events; training programmes cannot run as planned due to adverse weather, local/national events or political instability; National Disability Network members do not engage in the process of discussing and addressing the issue of carers. | Executive Director/Project Director
| ACTIVITY 6.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Biannual seminar held for relevant district authorities to gain recognition of the CAs and advocate for provision of carer specific services |  | 2 | 4 |  | Executive Director/Project Director
| ACTIVITY 6.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Staff of Carers Worldwide and senior staff of LEADS advocate to ensure needs and rights of carers becomes a standing agenda item at meetings of the National Disability Network | One off presentation to Network members regarding carers work | Representatives from Carers Associations attend a meeting and raise awareness around their needs and rights | Topics related to carers are discussed at every meeting |  | Executive Director/Project Director
| Carry out detailed baseline study using Carers Worldwide data collection tools as a means of measuring impact | Baseline data collected on 1,500 carers |  |  |  | Executive Director/Project Director