## Log Y1
ORGANISATION NAME | Joshua
PROJECT NAME | M'mera Mpoyamba/ Planting the seed' - Investing in Early Childhood Development in Malawi 4WU3-G8SX-LH
IMPACT | Impact Indicator 1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
Enhanced capacities in community-based childcare centres (CBCC) to reduce poverty through provision of improved nutrition, health and education to children aged 2-5 in Blantyre District | Percentage prevalence of stunting among children aged 2- 5 years reduced. Disaggregated by: male/female Numerator: Number of children with healthy BMI Denominator: Total children who had BMI measured Cumulative | Planned | 2% | 6/400 1.5% | 4/400 1% | 2/400 0.5%
Achieved
Source
Collection of Body Mass Index of children and MUAC Monthly health clinic statistics and analysis
| Impact Indicator 2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Percentage of children benefiting from improved standard of education/teaching in target CBCCs Disaggregated by: male/female Numerator: # of children regularly attending CBCC Denominator: Total number of children registered at CBCC Cumulative | Planned | 308 (55%) | 60% 360/600 (50%) | 70% 420/600 (50%) | 80% 480/600 (50%)
Achieved
Source
CBCC registers IDELA assessments
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumptions
Children aged 2-5 in GVH Malunga, Blantyre District with improved life outcomes, i.e. sufficiently and appropriately stimulated, well educated, healthy, well nourished and adequately protected | Number of children reached with improved ECD services through target CBCCs in GVH Malunga Disaggregated by: male/female Numerator: Number of children attending CBCC Denominator: Total number of children of CBCC age in target villages Cumulative | Planned | 308 | 400/676 (50%) | 500/676 (50%) | 600/676 (50%) | • Nutrition, health care and education inputs are sufficient to make significant impact on children's ECD outcomes. • ECD is supported at household level at well as CBCC. • Regular attendance at CBCC means child more likely to progress to primary school at age-appropriate time. • Economic factors at home do not hinder a child's progression into primary school at age-appropriate time. • Cognitive development priority for parents.
Achieved
Source
Enrolment and attendance records at CBCC level Training records Likuni Phala supply records Health Clinic records
| Outcome Indicator 2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Percentage & # of parents and caregivers who report cognitive change in child as a result of CBCC attendance Disaggregated by: age of children Numerator: Positive change reported by parents and caregivers Denominator: Number of parents and caregivers interviewed Cumulative | Planned | 120/ 150 80% | 128/150 90% | 138/150 92% | 143/150 95%
Achieved
Source
Key Informant Interviews / Focus Group Discussions
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 152471 |  |  |  |  | 152471 | 100%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumption
600 children in GVH Malunga meeting development milestones leading to greater preparedness for formal schooling | Percentage & # of children observed displaying age-appropriate social skills at targeted CBCCs (IDELA) Disaggregated by: male/female: age Numerator: Number of children Denominator: Total number of children observed using IDELA Cumulative | Planned | 41% (46%) | 140/200 70% (50%) | 160/200 80% (50%) | 180/200 90% (50%) | • The primary school has the capacity / places available for all the children who are ready to join the school • The child started at the CBCC at the age-appropriate time and has maximised on 3-4 years of pre-school exposure. • The greater the time the child has spent in the CBCC before age six, the greater the chance of their being prepared for school (exposure over 3-4 years to pre-school is more significant than the actual age at which the child starts school - causal relationship • Cognitive test is administered correctly • Caregivers have understood their training in child development milestones and can see the relationship between (a) motor skills and healthy development (b) the difference between answering a question and repeating an answer (moving away from rote learning)
Achieved
Source
Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations)
| Output Indicator 1.2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Percentage & # of children able to complete questions on an age appropriate test at targeted CBCCs (IDELA-Cognitive), Disaggregated by: male/female, age Numerator: Number of children Denominator: Total number of children assessed using IDELA Cumulative | Planned | 33% (37%) | 130/200 65% (50%) | 140/200 70% (50%) | 170/200 85% (50%)
Achieved
Source
Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations)
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
20% | Percentage & # of children observed displaying age-appropriate motor skills at targeted CBCCs (IDELA) Disaggregated by: male/female, age Numerator: Number of children Denominator: Total number of children assessed using IDELA Cumulative | Planned | 50% (52%) | 130/200 65% (50%) | 140/200 70% (50%) | 170/200 85% (50%)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 4836 |  |  |  |  | 4836 | 100
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumptions
Reduction in acute and severe and moderate malnutrition in children in GVH Malunga | Percentage & # of children presenting with a normal Mid Upper Arm Circumference for age bracket at targeted CBCC Disaggregated by: male/female, age Numerator: Number of children with green measurement on MUAC band Denominator: Total number of children measured using MUAC band Cumulative | Planned | 246/252 98% (40%) | 297/ 300 99% (50%) | 396/400 99% (50%) | 398/400 99.5% (50%) | • A child presenting with SAM / MAM has otherwise good attendance (relationship between low MUAC and attendance) • Consistency and accuracy in using the MUAC as a tool for measuring children's health and nutritional status • Spoilage of food stock is recorded and reported accurately • Consistency in referrals • DHO office is compliant in providing information • HSA has the capacity to support the nurse and health activities • Children who are referred actually follow up with the referral • The local health clinic has the capacity (staff & resources, specifically chiponde) to treat children referred with SAM
Achieved
Source
400 MUAC testing during termly general health monitoring session by the internal JOCC nurse
| Output Indicator 2.2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Number of children receiving daily fortified porridge at targeted CBCC Disaggregated by: male/female Nominator: Number of children attending CBCC Denominator: Number of children targeted by project Cumulative | Planned | 300/600 (56%) | 400/600 (50%) | 500/600 (50%) | 600/600 (50%)
Achieved
Source
CBCC attendance registers, food stock receipts, distribution records
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
20% | Number of children referred to health clinic for Moderate and Severe Acute Malnutrition (SAM) Disaggregated by: male/female, age Nominator: Number of children referred to DHO Denominator: Total number of children assessed for malnutrtion by JOCC Non-cumulative | Planned | 2% | 6/400 1.5% | 4/400 1% | 2/400 0.5%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | (1) Internal health visit records (2) District Health Office records via the Health Surveillance Officer and local clinic. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 40019 |  |  |  |  | 40019 | 100
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumption
60 caregivers with increased skills, self-esteem and earning potential | Percentage & # of caregivers reporting increased confidence in delivering ECD programme Disaggregated by: male/female, age Nominator: Number of caregivers who can cite differences in education activities as a result of training Denominator: Total number of caregivers active in 5 JOCC CBCC Cumulative | Planned | N/A | 18/30 60% (50%) | 21/30 70% (50%) | 27/30 85% (50%) | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.)
Achieved
Source
(1) FGD with caregivers (2) End of training evaluations (3) Key Informant Interviews
| Output Indicator 3.2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Number of caregivers trained in ECD and supporting activities Disaggregated by: male/female, age Nominator: Number of caregivers receiving completion certificate for training Denominator: Number of caregivers active in CBCC Cumulative | Planned | 5/30 (80%) | 20/30 (50%) | 25/30 (50%) | 30/30 (50%)
Achieved
Source
Training attendance records Caregiver KII
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
20% | Percentage & # of caregivers who are still in role and implementing key aspects of training at end of programme Disaggregated by: male/female, age Nominator: Number of caregivers staying active in CBCC for 3 years Denominator: Total number of caregivers Cumulative | Planned | N/A | 15/30 50% (50%) | 18/30 60% (50%) | 23/30 75% (50%)
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | (1) Daily attendance registers of caregivers (2) Classroom observations (3) Key Informant Interviews / FGD with caregivers |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 30169 |  |  |  |  | 30169 | 100
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumptions
Enhanced ECD capacity and knowledge among parents and community members with strong home-school partnerships developed | Number of parents attending and receiving training on well-being of children Disaggregated by male/female & age Nominator: Number of families having attended one or more training Denominator: Total number of families attending CBCC Cumulative | Planned | 0 | 200/500 (40%) | 250/500(50%) | 350/500 (60%) | • Content of training suitable for parents with a range of schooling backgrounds • Parents have resources to establish parenting associations • Other factors prohibiting parents involvement at CBCC are limited (economic, other commitments, etc.)
Achieved
Source
(1) Training attendance records (2) Pre/post training assessment
| Output Indicator 4.2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Percentage & # of parents actively engaged in the activities of the CBCCs Disaggregated by: male/female, age Nominator: Number of parents attending parent association meetings Denominator: Total number of families linked to CBCC over 3 years Cumulative | Planned |  | 100/500 20% | 150/500 30% | 200/ 500 40%
Achieved
Source
(1) CBCC records (2) KII with parents / caregivers (3) Observation by field monitor
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
10% | Number of centres with active parent associations (e) Nominator: Number of JOCC CBCC with regular minutes of meetings Denominator: Number ofJOCC CBCC involved in project Non-cumulative | Planned | N/A | 4 / 5 | 5 | 5
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | (1) Key Informant Interviews with parents (2) Observation by Field Monitor (3) Parent Associations minutes |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 12120 |  |  |  |  | 12120 | 100
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021) | Assumption
Five CBCCs with increased food security and 600 children with diversified diet | Number of garden committee members receiving permaculture and kitchen garden training Disaggregated by: male/female, age Nominator: Number of committee members completing training Denominator: Number of committee members Non-cumulative | Planned | 0 | 40/50 (50%) | 50/50 (50%) | 50/50 (50%) | • The landscape of the CBCC site will be suitable to food production • The groups are able to access enough water to sustain crops • The training translates into positive action by the garden club • The food grown is utilised as intended, for the diets of the children or sold to supplement income of CBCC • Caregivers have skills to use fresh produce in CBCC meals
Achieved
Source
(1) Training attendance records (2) Pre/post training assessment
| Output Indicator 5.2 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
| Number of CBCCs with active and productive kitchen gardens (f) Disaggregated by: N/A Nominator: Number of CBCCs producing 5 different crops Denominator: Number of CBCC Cumulative | Planned | 0 | 4 | 5 | 5
Achieved
Source
(1) KII with parents (2) Observation by field monitor (3) Records and KII with Garden Committee
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline (April 2018) | MTR (October 2019) | Milestone 2 (2020) | Target (March 2021)
10% | % & # of children receiving supplementary food from kitchen garden on a monthly basis Disaggregated: N/A Nominator: Number of meals recorded as using kitchen garden produce in one month Denominator: Total number of meals served in 5 CBCC in one month Cumulative | Planned | 0% | 40/100 40% | 50/100 50%% | 60/100 60%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | (1) KII with caregivers / parents (2) Observation by field monitor (3) Records and KII with Garden Committee |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 5711 |  |  |  |  | 5711 | 100
Definitions
(a) Benefiting defined as achieving 80% average IDELA score and attending CBCC for 75% of the time
(b) Improved ECD services defined as the combined provision of adequate nutrition and education. Adequate nutrition defined as 100g Likuni Phala per child per day (WFP guidelines) thus providing 70% of required daily micronutrients, supplemented with produce from CBCC garden. Adequate education defined as education delivered by trained caregivers who have access to, and are able to utilise, appropriate learning resources
(c) Caregivers must be completing 75% of scheduled rota and must be observed implementing specified activities (such as register, work stations, appropriate discipline etc.)
(d) Actively engaged defined as three of the below, or similar, being undertaken - parents giving feedback to caregivers, parents receiving feedback, parents ensuring child on time, parents sending children in with resource, parents attending event, parents looking in child book
(e) To be active they must have least 20 involved and having monthly meetings, evidence of minutes, evidence of some actions followed up.
(f) Active and productive defined as gardens that have at least 3 crops with high nutritional value under production in CBCC kitchen garden
Notes
(1) Indicator states number of children reached, and of that number what % were girls
(2) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(3) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(4) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(5) Indicator is % of children with a normal MUAC, alongside what % of these were girls
(6) Indicator is number of children and what % of this number are girls
(7) Indicator is number of children referred and what % of this number were girls
(8) Indicator is % of caregivers giving positive response and what % of these are female
(9) Indicator is number of caregivers and what % of this number are female
(10) Indicator is % of caregivers and what % of these are female
(11) Indicator is number of individuals and what % of this number are female
(12) Indicator is number of individuals and what % of this number are female

## Log Oct 2020
ORGANISATION NAME | Joshua
PROJECT NAME | M'mera Mpoyamba/ Planting the seed' - Investing in Early Childhood Development in Malawi 4WU3-G8SX-LH
IMPACT | Impact Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
nhanced capacity to reduce poverty through provision of improved nutition, health and education to children aged 2-5 in Blantyre district.This should be linked more to the Malawi / ECD / District level rather than the highest level of poverty … contribution to preschool childfrens development in Malawi... Linking this to the impact evaluation, there will be a small measurable contribution | Insert national level ECD indicator | Planned
Achieved
Source
| Impact Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Not necesary to have second one... only if relevant to impact evaluation.... | Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Children aged 2-5 in 5 catchment areas of GVH Malunga, Blantyre District with improved life outcomes, i.e. sufficiently and appropriately stimulated, well educated, healthy, well nourished and adequately protected Note: due to term date timings, some 6 year old children will also be included as they turn 6 late in the year and are part of the cohort below | Number of children reached with improved ECD services through target CBCCs in GVH Malunga Disaggregated by: male/female Numerator: Number of children attending CBCC Denominator: Total number of children of CBCC age in target villages Cumulative Suggested indicator: Number of children meeting developmental milestones through IDELA tool, disaggregated by age group: a) 3-4 year olds b) 5-6 year olds Note: This does not include data for children attending CBCCs who are not from the catchment area (such as Chingombe) Note: Sample size will be used... Insert detail of sample here | Planned |  | Reflect on ralistic targets expecting much smaller number in y1, to a much higher increase cumulatively by y3 |  |  | • Nutrition, health care and education inputs are sufficient to make significant impact on children's ECD outcomes. • ECD is supported at household level at well as CBCC. • Regular attendance at CBCC means child more likely to progress to primary school at age-appropriate time. • Economic factors at home do not hinder a child's progression into primary school at age-appropriate time. • Cognitive development priority for parents. what do we mean by this one? * Some children from the GVH will be attending private nurseries / this will not be a fixed number and should be monitoried a certain percentage of the children from the GVH are attending nurseries and that thiey stay attending Movement between nurseries and other JOCC CBBCs That all children enrolled are from that catchment area (not smuggled in)...
Achieved
Source
(1) Idela tool
| Outcome Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Percentage & # of parents and caregivers who report cognitive change in child as a result of CBCC attendance Disaggregated by: age of children Numerator: Positive change reported by parents and caregivers Denominator: Number of parents and caregivers interviewed Cumulative... This is interesting, but challenging for a parent to answer objectively... and the evidence of this is in the reality of attendance at CBCC...what is more interesting is absenteeism and linking this to health / hygiene and reasons why children might be absent (funeral, sickness, phala, etc) Suggested indicator: Number of children who are attending CBCC 90% or more of the time Note: This does not include data for children attending CBCCs who are not from the catchment area (such as Chingombe) AND also accounts for the children attending private nurseries | Planned | Denominator: What is the absolute total 2-6 years in Malunga catchment? (demominator) Total enrolment and regular attendance = numerator)
|  | Achieved |  | TBC
Source
Key Informant Interviews / Focus Group Discussions (1) Census data from HSA (2) Enrollment & attendance actuals at CBCC (3) Enrollment numbers from private nurseries (4) VDC reports on catchment numbers / household information
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 152471 |  |  |  |  | 152471 | 100%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
600 children in GVH Malunga meeting development milestones leading to greater preparedness for formal schooling REMOVE all of output 1 as it stands | Percentage & # of children observed displaying age-appropriate social skills at targeted CBCCs (IDELA) Disaggregated by: male/female: age Numerator: Number of children Denominator: Total number of children observed using IDELA Cumulative | Planned | 41% (46% F) | 140/200 70% (50% F) | 160/200 80% (50%) | 180/200 90% (50% F) | • The primary school has the capacity / places available for all the children who are ready to join the school • The child started at the CBCC at the age-appropriate time and has maximised on 3-4 years of pre-school exposure. • The greater the time the child has spent in the CBCC before age six, the greater the chance of their being prepared for school (exposure over 3-4 years to pre-school is more significant than the actual age at which the child starts school - causal relationship • Cognitive test is administered correctly • Caregivers have understood their training in child development milestones and can see the relationship between (a) motor skills and healthy development (b) the difference between answering a question and repeating an answer (moving away from rote learning)
|  | Achieved |  | TBC
Source
Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations)
| Output Indicator 1.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Percentage & # of children able to complete questions on an age appropriate test at targeted CBCCs (IDELA-Cognitive), Disaggregated by: male/female, age Numerator: Number of children Denominator: Total number of children assessed using IDELA Cumulative | Planned | 33% (37%) | 130/200 65% (50%F) | 140/200 70% (50% F) | 170/200 85% (50%)
|  | Achieved |  | TBC
Source
Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations)
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% | Percentage & # of children observed displaying age-appropriate motor skills at targeted CBCCs (IDELA) Disaggregated by: male/female, age Numerator: Number of children Denominator: Total number of children assessed using IDELA Cumulative | Planned | 50% (52%) | 130/200 65% (50%) | 140/200 70% (50%) | 170/200 85% (50%)
|  | Achieved |  | TBC
|  | Source |  |  |  |  | RISK RATING
|  | Observation of key social skills using IDELA tool and standard report format (Triangulated with key informant interviews with caregivers per centre and classroom observations) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 4836 |  |  |  |  | 4836 | 100
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
5 CBCCs have access to improved sanitation and hygiene facilities Access? Behaviour? Knowledge / training? What is actually being funded through the grant that is hygiene related? Then link this to formulation of the output / indicators | Something like … Children are observed using child-friendly latrines xx% of the time | Planned |  |  |  |  | • A child presenting with SAM / MAM has otherwise good attendance (relationship between low MUAC and attendance) • Consistency and accuracy in using the MUAC as a tool for measuring children's health and nutritional status • Spoilage of food stock is recorded and reported accurately • Consistency in referrals • DHO office is compliant in providing information • HSA has the capacity to support the nurse and health activities • Children who are referred actually follow up with the referral • The local health clinic has the capacity (staff & resources, specifically chiponde) to treat children referred with SAM
Achieved
Source
| Output Indicator 2.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Children observed using soap… Water & soap is out and being used | Planned
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% Recalculate all the weightings before resubmitting logframe | Number of children referred to health clinic for Moderate and Severe Acute Malnutrition (SAM) Disaggregated by: male/female, age Nominator: Number of children referred to DHO Denominator: Total number of children assessed for malnutrtion by JOCC Non-cumulative | Planned | 2% | 6/600 1.5% | 4/600 1% | 2/600 0.5%
|  | Achieved |  | 2/600
|  | Source |  |  |  |  | RISK RATING
|  | (1) Internal health visit records (2) District Health Office records via the Health Surveillance Officer and local clinic. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 40019 |  |  |  |  | 40019 | 100
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
60 caregivers with increased skills, self-esteem and earning potential 50 caregivers have increased skills and knowledge in child development through: a) Child protection and safeguarding b) Behaviour management c) TALULAR d) Speach, language and communcation e) Numeracy f) Child Development .... TEAM TO REFLECT ON LIST & CLUSTER | Percentage & # of caregivers reporting increased confidence in delivering ECD programme Disaggregated by: male/female, age Nominator: Number of caregivers who can cite differences in education activities as a result of training Denominator: Total number of caregivers active in 5 JOCC CBCC Cumulative Caregivers demonstrate increased skills and knowledge in the relevant training | Planned | N/A | 18/30 60% (50%) | 21/30 70% (50%) | 27/30 85% (50%) | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.) RETHINK THESE BASED ON REVISED OUTPUT Training inputs ... will lead to the expected change (many influencing factors will mean that not everyone will take in the knowledge... Retention factors ... That enough of those trained will stay and implement jOSHUA TO REVIEW
|  | Achieved |  | TBC
Source
(1) FGD with caregivers (2) Pre/post training tests (3) Key Informant Interviews
| Output Indicator 3.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Something that demonstrates the observed changes in the learning enviroment… Such as: Timetables are being used 80% of the time (Disaggregated by CBCC) Joshua to think about this one and refine… Its in the regular field monitoring that this will be observed... Interactions with children, timetables, learning journeys, resources being used, etc | Planned
Achieved
Source
(1) Observations at CBCC
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% | Drop out rates of trained caregivers each term Disaggregated by Gender, age, length of service, Nominator: Number of caregivers staying active in CBCC for 3 years Denominator: Total number of caregivers Cumulative | Planned | N/A | 15/30 50% (50%) | 18/30 60% (50%) | 23/30 75% (50%)
|  | Achieved |  | 26/30 80% (60%)
|  | Source |  |  |  |  | RISK RATING
|  | (1) Caregiver attendance registers (2) Key Informant Interviews / FGD with caregivers |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 30169 |  |  |  |  | 30169 | 100
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Enhanced ECD capacity and knowledge among parents and community members with strong home-school partnerships developed | Parents / guardians demonstrate increased skills and knowledge in the relevant training Number of parents attending and receiving training on well-being of children Disaggregated by male/female & age Nominator: Number of families having attended one or more training Denominator: Total number of families attending CBCC Cumulative | Planned | 0 | 200/500 (40%) | 250/500(50%) | 350/500 (60%) | • Content of training suitable for parents with a range of schooling backgrounds • Parents have resources to establish parenting associations • Other factors prohibiting parents involvement at CBCC are limited (economic, other commitments, etc.)
|  | Achieved |  | 300/500 60% (70%)
Source
(1) Training attendance records (2) Pre/post training assessment - think about how realistic is this … what approach works best… Outline that here (Sue mentions group work, mapping out knowledge) This will be more Qualitative.. mix of questions at end of trainings... Feedback from the training provider...
| Output Indicator 4.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Percentage & # of parents actively engaged in the activities of the CBCCs Disaggregated by: male/female, age Nominator: Number of parents attending parent association meetings Denominator: Total number of families linked to CBCC over 3 years Cumulative Perhaps a qualitative indicator here around parent perceptions | Planned |  | 100/500 20% | 150/500 30% | 200/ 500 40%
|  | Achieved |  | 100/500 (estimate)
Source
(1) CBCC records (2) KII with parents / caregivers (3) Observation by field monitor
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
10% | Number of centres with active parent associations DEFINE ACTIVE MORE CLEARLY… PTA committes meeting a minimum of members can name xx number of Nominator: Number of JOCC CBCC with regular minutes of meetings Denominator: Number ofJOCC CBCC involved in project Non-cumulative | Planned | N/A | 5 / 5 | 5 | 5
|  | Achieved |  | 5.5.
|  | Source |  |  |  |  | RISK RATING
|  | (1) Key Informant Interviews with parents (2) Observation by Field Monitor (3) Parent Associations minutes fgd WITH PARENTS |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 12120 |  |  |  |  | 12120 | 100
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Five CBCC with increased food security, and 600 children with diversified diet Increased food security and diversified diets across all five CBCC Inputs: Phala, kitchen garden training, tools, seeds, etc Perhaps include a footnote about briquettes somewhere, that this is something the project is working towards & may not be possible within this project | Number of garden committee members receiving permaculture and kitchen garden training Disaggregated by: male/female, age Nominator: Number of committee members completing training Denominator: Number of committee members Non-cumulative Number of times a kitchen garden can produce food each term for ech CBCC, through a) Food b) Cash for food Joshua to reflect on how the income generation element might best be captured to show sustainability - this is a hugely positive impact / change | Planned | 0 | 40/50 (50%) | 50/50 (50%) | 50/50 (50%) | • The landscape of the CBCC site will be suitable to food production • The groups are able to access enough water to sustain crops • The training translates into positive action by the garden club • The food grown is utilised as intended, for the diets of the children or sold to supplement income of CBCC • Caregivers have skills to use fresh produce in CBCC meals
|  | Achieved |  | 40/50
Source
(1) Training attendance records (2) Pre/post training assessment
| Output Indicator 5.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of CBCCs with active and productive kitchen gardens (f) Remove as the above captures this E.g: Number of days children eat phala at the CBCC (need to calculate school days & factor in holidays, availability & other issues - firewood etc) then set a realistic but ambitious target (disaggregated by CBCC) | Planned | 0 | 5 | 5 | 5
|  | Achieved |  | 0
Source
(1) KII with parents (2) Observation by field monitor (3) Records and KII with Garden Committee
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
10% | % & # of children receiving supplementary food from kitchen garden on a monthly basis Disaggregated: Nominator: Number of meals recorded as using kitchen garden produce in one month Denominator: Total number of meals served in 5 CBCC in one month Cumulative captured above | Planned | 0% | 40/100 40% | 50/100 50%% REVIEW | 60/100 60%
|  | Achieved |  | TBC
|  | Source |  |  |  |  | RISK RATING
|  | (1) KII with caregivers / parents (2) Observation by field monitor (3) Records and KII with Garden Committee |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 5711 PLEASE REVIEW ALL THE AMOUNT ONCE COMPLETED REVISIONS |  |  |  |  | 5711 | 100
Definitions - PLEASE REVIEW THESE & DELETE AS MUCH AS POSSIBLE, TRY TO CAPTURE WITHIN THE LOGFRAME ITSELF
(a) Benefiting defined as achieving 80% average IDELA score and attending CBCC for 75% of the time
(b) Improved ECD services defined as the combined provision of adequate nutrition and education. Adequate nutrition defined as 100g Likuni Phala per child per day (WFP guidelines) thus providing 70% of required daily micronutrients, supplemented with produce from CBCC garden. Adequate education defined as education delivered by trained caregivers who have access to, and are able to utilise, appropriate learning resources
(c) Caregivers must be completing 75% of scheduled rota and must be observed implementing specified activities (such as register, work stations, appropriate discipline etc.)
(d) Actively engaged defined as three of the below, or similar, being undertaken - parents giving feedback to caregivers, parents receiving feedback, parents ensuring child on time, parents sending children in with resource, parents attending event, parents looking in child book
(e) To be active they must have least 20 involved and having monthly meetings, evidence of minutes, evidence of some actions followed up.
(f) Active and productive defined as gardens that have at least 3 crops with high nutritional value under production in CBCC kitchen garden
Notes
(1) Indicator states number of children reached, and of that number what % were girls
(2) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(3) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(4) Indicator is the average IDELA score (%) for the group, alongside the average IDELA score (%) for girls
(5) Indicator is % of children with a normal MUAC, alongside what % of these were girls
(6) Indicator is number of children and what % of this number are girls
(7) Indicator is number of children referred and what % of this number were girls
(8) Indicator is % of caregivers giving positive response and what % of these are female
(9) Indicator is number of caregivers and what % of this number are female
(10) Indicator is % of caregivers and what % of these are female
(11) Indicator is number of individuals and what % of this number are female
(12) Indicator is number of individuals and what % of this number are female

## Jan 2020
ORGANISATION NAME | Joshua Orphan and Community Care
PROJECT NAME | M'mera Mpoyamba/ Planting the seed' - Investing in Early Childhood Development in Malawi 4WU3-G8SX-LH
IMPACT | Impact Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
Malawian children aged 2-6 access comprehensive and effective community-based ECD which supports their nutrition, health and education | Number of children reached with improved package of ECD services, disaggregated by gender | Planned | 308 | 400/600 66% | 500/600 83% | 600/600 100%
|  | Achieved |  | 487/600
Source
Enrolment and attendance actuals at CBCC. Enrolment figures from private nurseries. VDC reports on catchment numbers. Census data from HAS.
| Impact Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Children aged 2-6 living in 5 catchment areas of GVH Malunga (Blantyre District) are developmentally on track and ready for transition to primary school | Number of children meeting development milestones, disaggregated by gender and age group (3-4 years, 5-6 years) | Planned | 41% (46% F) | 140/200 70% (50% F) | 160/200 80% (50%) | 180/200 90% (50% F) | Nutrition, health care and education inputs are sufficient to make significant difference to children's ECD outcomes. ECD is supported at household level as well as CBCC. Regular attendance at CBCC means child more likely to progress to primary school at appropriate time. Economic circumstances at home do not hinder a childs progression to primary school
|  | Achieved |  | Not available
Source
IDELA assessments
| Outcome Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of children enrolled in primary school and still attending at the end of their first year, disaggregated by gender | Planned | Not available | Not available | 150 | 200
|  | Achieved |  | 55 (62% | 155 (52%)
Source
Primary school enrolment records. Primary school registration data.
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 152471 |  |  |  |  | 152471 | 100%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Creation of safe, inclusive and sustainable learning environments at 5 CBCC | Number of locally and commercially made resources available and used in individual CBCC, disaggregated by type and learning outcome | Planned | 0 | 15 | 25 | 35 | • The primary school has the capacity / places available for all the children who are ready to join the school • The child started at the CBCC at the age-appropriate time and has maximised on 3-4 years of pre-school exposure. • The greater the time the child has spent in the CBCC before age six, the greater the chance of their being prepared for school (exposure over 3-4 years to pre-school is more significant than the actual age at which the child starts school - causal relationship • Cognitive test is administered correctly • Caregivers have understood their training in child development milestones and can see the relationship between (a) motor skills and healthy development (b) the difference between answering a question and repeating an answer (moving away from rote learning)
Achieved
Source
Monthly checklist completed by Field Officers & caregivers .
| Output Indicator 1.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of children with disabilities enrolled and attending CBCC 60% or more of the time when CBCC is open | Planned | 0 | 4 | 5 | 5
|  | Achieved |  | 4 | 2
Source
CBCC registers and enrolment records.
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
30% | Average hours per month of age appropriate differentiated education activities delivered in each CBCC, disaggregated by age group | Planned | 0 | 20 | 30 | 40
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | CBCC timetables. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 4836 |  |  |  |  | 4836 | 100
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Improved health and nutrition monitoring, hygiene and sanitation at 5 CBCC | Number of children (monthly average) observed using child-friendly latrines after mealtimes during CBCC sessions | Planned |  |  | 15 | 30 | • A child presenting with SAM / MAM has otherwise good attendance (relationship between low MUAC and attendance) • Consistency and accuracy in using the MUAC as a tool for measuring children's health and nutritional status • Consistency in referrals • DHO office is compliant in providing information • HSA has the capacity to support • Children who are referred follow up with the referral • The local health clinic has the capacity (staff & resources, specifically chiponde) to treat children referred with SAM Presence of latrines/handwashing facilities encourages usage Soap is used for handwashing and not misappropriated
Achieved
Source
Monitoring checklist completed by field officers and caregivers.
| Output Indicator 2.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of bars of soap used and replenished for handwashing and utensil washing at CBCC per term (actual use/expected use) | Planned | 10 | 10 | 16 | 20
|  | Achieved |  | Not available
Source
Monitoring checklist completed by field officers and caregivers. Project records and accounts.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% | Number of children referred to health clinic for Moderate and Severe Malnutrition, disaggregated by age and gender | Planned | 2% | 6/600 1.5% | 4/600 1% | 2/600 0.5%
|  | Achieved |  | 2/600
|  | Source |  |  |  |  | RISK RATING
|  | Mobile health clinic records. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 40019 |  |  |  |  | 40019 | 100
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Caregivers empowered with knowledge and skills on ECD and able to lead daily activities at CBCC | Number of externally trained caregivers who demonstrate increased skills and ECD knowledge, disaggregated by gender | Planned | 0 | 15/30 | 20/30 | 25/30 | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.) Training inputs lead to the expected change Enough trained caregivers remain in post to be able to make change,
Achieved
Source
FGD with caregivers. Pre/post training tests. Key Informant Interviews
| Output Indicator 3.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of caregivers demonstrating good practice in safeguarding, session planning and CBCC management, disaggregated by gender | Planned | 0/30 | Not available | 20 | 30
|  | Achieved |  | Not available
Source
CBCC timetables. Field officer observations at CBCC. Key informant interviews.
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
30% | Number of trained caregivers still in position over lifetime of project, disaggregated by gender | Planned | N/A | 15/30 50% (50%) | 18/30 60% (50%) | 23/30 75% (50%)
|  | Achieved |  | 26/30 80% (60%)
|  | Source |  |  |  |  | RISK RATING
|  | Caregiver attendance registers. Key Informant Interviews / FGD with caregivers |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 30169 |  |  |  |  | 30169 | 100
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Increased community engagement, involvement in and ownership of ECD activities at CBCC | Number of children attending CBCC 80% of possible days per quarter, disaggregated by gender | Planned |  | 400 | 450 | 480 | • Content of training suitable for parents with a range of schooling backgrounds • Parents have resources to establish parenting associations • Other factors prohibiting parents involvement at CBCC are limited (economic, other commitments, etc.)
|  | Achieved |  | 317
Source
Register and enrolment data.
| Output Indicator 4.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of centres with active parent associations (minimum of 20 families involved, monthly meeting attendance, and evidence of actions followed up). | Planned | N/A | 2/5 | 4/5 | 5/5
|  | Achieved |  | 3 | 4 | 5
Source
Minutes of PTA meetings. Key informant interviews
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
15% | Number of centres with active management committee (10 elected members who attend regularly,( 3/4 )minutes kept of meetings and evidence of actions followed up). | Planned | N/A | 2/5 | 4/5 | 5/5
|  | Achieved |  | 4 | 4 | 5
|  | Source |  |  |  |  | RISK RATING
|  | Minutes of management committee meetings. Key Informant Interviews |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 12120 |  |  |  |  | 12120 | 100 | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.) Training inputs lead to the expected change Enough trained caregivers remain in post to be able to ma+C77:G86ke change,
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Increased food security and diversification of diet for children attending 5 CBCC | Number of days CBCC kitchen garden provides food or cash for food per term | Planned | 0 | 3 | 12 | 18 | • The landscape of the CBCC site suitable to food production • The groups are able to access enough water to sustain crops • The training translates into positive action by the garden club • The food grown is utilised as intended, for the diets of the children or sold to supplement income of CBCC • Caregivers have skills to use fresh produce in CBCC meals
Achieved
Source
(1) Food distribution records (2) CBCC accounts
| Output Indicator 5.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of days children eat likuni phala at CBCC per term when CBCC is open | Planned | 0 | 40 | 50 | 60
Achieved
Source
Food purchase and distribution records. CBCC attendance records.
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
15% | Number of gardeners receiving permaculture and kitchen gardening training, disaggregated by gender | Planned | 0 | 40 (50%) | 50 (50%) | 50
|  | Achieved |  | 15 (60%)) | 30 (60%)
|  | Source |  |  |  |  | RISK RATING
|  | Kitchen garden records. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 5711 |  |  |  |  | 5711 | 100
Notes
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data being collected Feb/March 2020
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data collection Oct 2019

## APRIL 2020
ORGANISATION NAME | Joshua Orphan and Community Care
PROJECT NAME | M'mera Mpoyamba/ Planting the seed' - Investing in Early Childhood Development in Malawi 4WU3-G8SX-LH
IMPACT | Impact Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
Malawian children aged 2-6 access comprehensive and effective community-based ECD which supports their nutrition, health and education | Number of children reached with improved package of ECD services, disaggregated by gender | Planned | 308 | 400/600 | 500/600 | 600/600
|  | Achieved |  | 487/600 | 627/600 (50% F) | 687/600 (50% F)
Source
Enrolment and attendance actuals at CBCC. Enrolment figures from private nurseries. VDC reports on catchment numbers. Census data from HAS.
| Impact Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Children aged 2-6 living in 5 catchment areas of GVH Malunga (Blantyre District) are developmentally on track and ready for transition to primary school | Number of children meeting development milestones, disaggregated by gender and age group (3-4 years, 5-6 years) | Planned | 82/200 (46% F) | 140/200 70% (50% F) | 160/200 80% (50%) | 180/200 90% (50% F) | Nutrition, health care and education inputs are sufficient to make significant difference to children's ECD outcomes. ECD is supported at household level as well as CBCC. Regular attendance at CBCC means child more likely to progress to primary school at appropriate time. Economic circumstances at home do not hinder a childs progression to primary school
|  | Achieved |  | Not available | 141/200 (50%) | 189/200 (50% F)
Source
IDELA assessments
| Outcome Indicator 2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of children enrolled in primary school and still attending at the end of their first year, disaggregated by gender | Planned | Not available | Not available | 150 | 150
|  | Achieved |  | 55 (62% | 155 (52%) | 190
Source
Primary school enrolment records. Primary school registration data.
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 152471 |  |  |  |  | 152471 | 100%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Creation of safe, inclusive and sustainable learning environments at 5 CBCC | Number of locally and commercially made resources available and used in individual CBCC, disaggregated by type and learning outcome | Planned | 0 | 15 | 25 | 25 | • The primary school has the capacity / places available for all the children who are ready to join the school • The child started at the CBCC at the age-appropriate time and has maximised on 3-4 years of pre-school exposure. • The greater the time the child has spent in the CBCC before age six, the greater the chance of their being prepared for school (exposure over 3-4 years to pre-school is more significant than the actual age at which the child starts school - causal relationship • Cognitive test is administered correctly • Caregivers have understood their training in child development milestones and can see the relationship between (a) motor skills and healthy development (b) the difference between answering a question and repeating an answer (moving away from rote learning)
|  | Achieved |  | N/A | 26 | 28
Source
Monthly checklist completed by Field Officers & caregivers .
| Output Indicator 1.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of children with disabilities enrolled and attending CBCC 60% or more of the time when CBCC is open | Planned | 0 | 4 | 5 | 5
|  | Achieved |  | 4 | 2 | 5
Source
CBCC registers and enrolment records.
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
30% | Average hours per month of age appropriate differentiated education activities delivered in each CBCC, disaggregated by age group | Planned | 0 | 20 | 30 | 30
|  | Achieved |  | NA | 30 | 36
|  | \ |  |  |  |  | RISK RATING
|  | CBCC timetables. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 4836 |  |  |  |  | 4836 | 100
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Improved health and nutrition monitoring, hygiene and sanitation at 5 CBCC | Number of children (monthly average) observed using child-friendly latrines after mealtimes during CBCC sessions | Planned |  |  | 15 | 30 | • A child presenting with SAM / MAM has otherwise good attendance (relationship between low MUAC and attendance) • Consistency and accuracy in using the MUAC as a tool for measuring children's health and nutritional status • Consistency in referrals • DHO office is compliant in providing information • HSA has the capacity to support • Children who are referred follow up with the referral • The local health clinic has the capacity (staff & resources, specifically chiponde) to treat children referred with SAM Presence of latrines/handwashing facilities encourages usage Soap is used for handwashing and not misappropriated
|  | Achieved |  |  | 13 | 25
Source
Monitoring checklist completed by field officers and caregivers.
| Output Indicator 2.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of bars of soap used and replenished for handwashing and utensil washing at CBCC per term (actual use/expected use) | Planned | 10 | 10 | 16 | 20
|  | Achieved |  | Not available | 18 | 20
Source
Monitoring checklist completed by field officers and caregivers. Project records and accounts.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% | Number of children referred to health clinic for Moderate and Severe Malnutrition, disaggregated by age and gender | Planned | 2% | 6/600 1.5% | 4/600 1% | 2/600 0.5%
|  | Achieved |  | 2/600 | 2/600 | 0.5 (51)
|  | Source |  |  |  |  | RISK RATING
|  | Mobile health clinic records. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 40019 |  |  |  |  | 40019 | 100
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Caregivers empowered with knowledge and skills on ECD and able to lead daily activities at CBCC | Number of externally trained caregivers who demonstrate increased skills and ECD knowledge, disaggregated by gender | Planned | 0 | 15/30 | 20/30 | 25/30 | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.) Training inputs lead to the expected change Enough trained caregivers remain in post to be able to make change,
|  | Achieved |  |  | 10/30 (8 female) | 20 (8 male)
Source
FGD with caregivers. Pre/post training tests. Key Informant Interviews
| Output Indicator 3.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of caregivers demonstrating good practice in safeguarding, session planning and CBCC management, disaggregated by gender | Planned | 0/30 | Not available | 20 | 25
|  | Achieved |  | Not available | 20 (16 female) | 25
Source
CBCC timetables. Field officer observations at CBCC. Key informant interviews.
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
20% | Number of trained caregivers still in position over lifetime of project, disaggregated by gender | Planned | N/A | 15/30 50% (50%) | 18/30 60% (50%) | 23/30 75% (50%)
|  | Achieved |  | 26/30 80% (60%) | 24/30 | 23
|  | Source |  |  |  |  | RISK RATING
|  | Caregiver attendance registers. Key Informant Interviews / FGD with caregivers |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 30169 |  |  |  |  | 30169 | 100
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumptions
Increased community engagement, involvement in and ownership of ECD activities at CBCC | Number of children attending CBCC 80% of possible days per quarter, disaggregated by gender | Planned |  | 400 | 450 | 480 | • Content of training suitable for parents with a range of schooling backgrounds • Parents have resources to establish parenting associations • Other factors prohibiting parents involvement at CBCC are limited (economic, other commitments, etc.)
|  | Achieved |  | 317 | 312 | 434
Source
Register and enrolment data.
| Output Indicator 4.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of centres with active parent associations (minimum of 20 families involved, monthly meeting attendance, and evidence of actions followed up). | Planned | N/A | 2/5 | 4/5 | 5/5
|  | Achieved |  | 3 | 5 | 5
Source
Minutes of PTA meetings. Key informant interviews
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
15% | Number of centres with active management committee (10 elected members who attend regularly,( 3/4 )minutes kept of meetings and evidence of actions followed up). | Planned | N/A | 2/5 | 4/5 | 5/5
|  | Achieved |  | 4 | 5 | 5
|  | Source |  |  |  |  | RISK RATING
|  | Minutes of management committee meetings. Key Informant Interviews |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 12120 |  |  |  |  | 12120 | 100 | • Content of training suitable for caregivers with a range of formal schooling backgrounds • Caregivers have resources to implement new methods from the training • Caregivers able to adapt generic training to their own CBCC context • Training motivates caregivers to continue volunteering at CBCC • Incentives are sufficient to motivate trained caregivers to stay at CBCC for reasonable period • Other factors prohibiting caregivers from attending / staying at CBCC are limited (economic, other commitments, etc.) Training inputs lead to the expected change Enough trained caregivers remain in post to be able to ma+C77:G86ke change,
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021 | Assumption
Increased food security and diversification of diet for children attending 5 CBCC | Number of days CBCC kitchen garden provides food or cash for food per term | Planned | 0 | 3 | 12 | 18 | • The landscape of the CBCC site suitable to food production • The groups are able to access enough water to sustain crops • The training translates into positive action by the garden club • The food grown is utilised as intended, for the diets of the children or sold to supplement income of CBCC • Caregivers have skills to use fresh produce in CBCC meals
|  | Achieved |  | NA | 2 | 10
Source
(1) Food distribution records (2) CBCC accounts
| Output Indicator 5.2 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
| Number of days children eat likuni phala at CBCC per term when CBCC is open | Planned | 0 | 40 | 50 | 60
|  | Achieved |  |  | 50 | 60
Source
Food purchase and distribution records. CBCC attendance records.
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline (April 2018) | Milestone 1 March 2019 | Milestone 2 March 2020 | Milestone 3 April 2021
15% | Number of gardeners receiving permaculture and kitchen gardening training, disaggregated by gender | Planned | 0 | 40 (50%) | 50 (50%) | 50
|  | Achieved |  | 15 (60%)) | 30 (60%) | 50
|  | Source |  |  |  |  | RISK RATING
|  | Kitchen garden records. |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Appeal income (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 5711 |  |  |  |  | 5711 | 100
Notes
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data being collected Feb/March 2020
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data collection Oct 2019

## Change Tab
All changes to logframe (including indicators, milestone targets, achievements, assumptions, etc) should be noted here, and should be agreed and signed off by PRM during change windows (not within 3 months of annual review or PCR). Changes should be made in a new unlocked tab, in RED until approved
| Change tab | Date of change request | Current | Changing to | Justification | Liz Wambugu. Approved 26.03.2020
# | Example: Outcome Indicator 1.1 | 2019-11-06 | Paste word for word from logframe | Sugggest new wording | Give justification for change
1 | Impact | 2020-01-21 | Children aged 2-5 in 5 catchment areas of GVH Malunga, Blantyre District with improved life outcomes, i.e. sufficiently and appropriately stimulated, well educated, healthy, well nourished and adequately protected | Malawian children aged 2-6 access comprehensive and effective community-based ECD which supports their nutrition, health and education
2 | Outcome | 2020-01-21 | 600 children in GVH Malunga meeting development milestones leading to greater preparedness for formal schooling | Children aged 2-6 living in 5 catchment areas of GVH Malunga (Blantyre District) are developmentally on track and ready for transition to primary school
3 | Output 1 | 2020-01-21 | 600 children in GVH Malunga meeting development milestones leading to greater preparedness for formal schooling | Creation of safe, inclusive and sustainable learning environments at 5 CBCC | More accurately reflects what project activities are aiming to achieve and reflects project inputs.
4 | Output 2 | 2020-01-21 | Reduction in acute and severe and moderate malnutrition in children in GVH Malunga | Improved health and nutrition monitoring, hygiene and sanitation at 5 CBCC | Includes WASH outputs so reflects project inputs
5 | Output 3 | 2020-01-21 | 60 caregivers with increased skills, self-esteem and earning potential | Caregivers empowered with knowledge and skills on ECD and able to lead daily activities at CBCC
6 | Output 4 | 2020-01-21 | Enhanced ECD capacity and knowledge among parents and community members with strong home-school partnerships developed | Increased community engagement, involvement in and ownership of ECD activities at CBCC
7 | Output 5 | 2020-01-21 | Five CBCC with increased food security, and 600 children with diversified diet | Increased food security and diversification of diet for children attending 5 CBCC
8 | Impact Indicator 1 | 2020-01-21 | Percentage prevalence of stunting among children aged 2- 5 years reduced. | Number of children reached with improved package of ECD services (disaggregated by gender)
9 | Impact Indicator 2 | 2020-01-21 | Percentage of children benefiting from improved standard of education/teaching in target CBCCs | Proposed deletion.
10 | Outcome Indicator 1 | 2020-01-21 | Number of children reached with improved ECD services through target CBCCs in GVH Malunga | Number of children meeting development milestones (disaggregated by age group 3-4 years, 5-6 years)
11 | Outcome Indicator 2 | 2020-01-21 | Percentage & # of parents and caregivers who report cognitive change in child as a result of CBCC attendance | Number of children attending CBCC 80% of the time (disaggregated by gender)
12 | Output Indicator 1.1. | 2020-01-21 | Percentage & # of children observed displaying age-appropriate social skills at targeted CBCCs (IDELA) | Number of CBCC resources used in education activities (disaggregated by cost, safety, inclusion and sustainability)
13 | Output Indicator 1.2 | 2020-01-21 | Percentage & # of children able to complete questions on an age appropriate test at targeted CBCCs (IDELA-Cognitive) | Number of children with additional needs enrolled and attending CBCC 50% or more of the time.
14 | Output Indicators 1.3 | 2020-01-21 | Percentage & # of children observed displaying age-appropriate motor skills at targeted CBCCs (IDELA) | Children participate in age appropriate differentiated education activities for 60% of the CBCC timetable (disaggregated by age)
15 | Output Indicator 2.1 | 2020-01-21 | Percentage & # of children presenting with a normal Mid Upper Arm Circumference for age bracket at targeted CBCC
16 | Output Indicator 2.2 | 2020-01-21 | Number of children receiving daily fortified porridge at targeted CBCC
17 | Output Indicators 2.3 | 2020-01-21 | Number of children referred to health clinic for Moderate and Severe Acute Malnutrition (SAM)
18 | Output Indicator 3.1 | 2020-01-21 | Percentage & # of caregivers reporting increased confidence in delivering ECD programme | Number of Caregivers who demonstrate increased skills and knowledge in training delivered
19 | Output Indicator 3.2 | 2020-01-21 | Number of caregivers trained in ECD and supporting activities | Caregivers completing 75% of scheduled rota and observed implementing specified activities (register, work stations, behaviour management)
20 | Output Indicator 3.3 | 2020-01-21 | Percentage & # of caregivers who are still in role and implementing key aspects of training at end of programme | % retention of trained caregivers over lifetime of project
21 | Output Indicator 4.1 | 2020-01-21 | Number of parents attending and receiving training on well-being of children | Number of Parents and guardians demonstrate increased skills and knowledge as a result of training
22 | Output Indicator 4.2 | 2020-01-21 | Percentage & # of parents and community members actively engaged in the activities of the CBCCs | Number of action plans developed and acted upon disaggregated by those from parents association and management committee.
23 | Output Indicator 4.3 | 2020-01-21 | Number of centres with active parent associations | Proposed deletion
24 | Output Indicator 5.1 | 2020-01-21 | Number of garden committee members receiving permaculture and kitchen garden training | Number of times CBCC kitchen garden provides food or cash for food per term
25 | Output Indicator 5.2 | 2020-01-21 | Number of CBCCs with active and productive kitchen gardens | Number of days children eat likuni phala in CBCC per term
26 | Output Indicator 5.3 | 2020-01-21 | % & # of children receiving supplementary food from kitchen garden on a monthly basis | Number of Kitchen gardens with at least 3 crops with high nutritional value under production (disaggregated by crops)
27 | Assumption |  |  | Cognitive Development priority for parents | Lack of clarity
28
29
30
31
32
33
34
35

## Additional Data (hidden)
Enrolment Data
CBCC | Girls | Boys | Total | Estimated 20% not yet reached
Kaliati | 45 | 47 | 92 | 110.4
Daniel | 43 | 45 | 88 | 105.6
Ching'ombe | 66 | 67 | 133 | 159.6
Chilaweni | 54 | 73 | 127 | 152.4
Maso | 60 | 63 | 123 | 147.6
Total | 268 | 295 | 563 | 675.6
Caregiver Data
CBCC | Female | Male | 15 - 24 | 25 - 49 | 50 - 64 | Over 65 | Disabled | Total
Kaliati | [7 empty] | 0
Daniel | [7 empty] | 0
Ching'ombe | [7 empty] | 0
Chilaweni | [7 empty] | 0
Maso | [7 empty] | 0
Total | [7 empty] | 0
Garden Committee Data
CBCC | Female | Male | 15 - 24 | 25 - 49 | 50 - 64 | Over 65 | Disabled | Total
Kaliati | [7 empty] | 0
Daniel | [7 empty] | 0
Ching'ombe | [7 empty] | 0
Chilaweni | [7 empty] | 0
Maso | [7 empty] | 0
Total | [7 empty] | 0
Parent Association Data
CBCC | Female | Male | 15 - 24 | 25 - 49 | 50 - 64 | Over 65 | Disabled | Total
Kaliati | [7 empty] | 0
Daniel | [7 empty] | 0
Ching'ombe | [7 empty] | 0
Chilaweni | [7 empty] | 0
Maso | [7 empty] | 0
Total | [7 empty] | 0
FGD Composition
CBCC | Caregivers |  |  | Parents |  |  | Garden
| Female | Male | Total | Mothers | Fathers | Total | Female | Male | Total
Kaliati | 3 | 0 | 3 | 5 | 4 | 9 | 4 | 1 | 5
Daniel | 4 | 0 | 4 | 5 | 4 | 9 | 0 | 4 | 4
Ching'ombe | 4 | 1 | 5 | 5 | 5 | 10 | 1 | 4 | 5
Chilaweni | 4 | 1 | 5 | 5 | 5 | 10 | 4 | 0 | 4
Maso | 4 | 1 | 5 | 8 | 4 | 12 | 2 | 2 | 4
Total | 19 | 3 | 22 | 28 | 22 | 50 | 11 | 11 | 22
Impact Indicator 1 | Logframe data | Children attending health check | MAM / SAM
|  | Total | Boys | Girls | Total
Percentage prevalence of stunting among children aged 2- 5 years (reduction) | 2% | 252 | 3 | 2 | 5
Outcome Indicator 2 | Logframe data | Total Parents / Caregivers | Number positive response
Percentage of parents and caregivers who report cognitive change in child as a result of CBCC attendance | 80% | 72 | 14
Output Indicator 1.1, 1.2, 1.3 | Logframe data | Boys score | Girls Score
Percentage of children observed displaying age-appropriate social skills at targeted CBCCs (IDELA), (disaggregated by gender, % girls) (2) | 41% (46%) | 37% | 46%
Percentage of children able to complete questions on an age appropriate test at targeted CBCCs (IDELA-Cognitive), (disaggregated by gender, % girls) (3) | 33% (37%) | 29% | 37%
Percentage of children observed displaying age-appropriate motor skills at targeted CBCCs (IDELA), (disaggregated by gender, % girls) (4) | 50% (52%) | 48% | 52%
Output Indicator 2.1 | Logframe data | Children attending health check | Number of children referred
|  | Total | Boys | Girls | Total
Percentage of children presenting with a normal Mid Upper Arm Circumference for age bracket at targeted CBCCs, (disaggregated by gender, % girls) (5) | 98% (40%) | 252 | 3 | 2 | 5
Output Indicator 2.2 | Logframe data | Total children enrolled | Boys enrolled | Girls enrolled | Estimated children in target area
Number of children receiving daily fortified porridge at targeted CBCCs, (disaggregated by gender, % girls) (6) | 300 (56%) | 563 | 295 | 268 | 676
Output Indicator 2.3 | Logframe data | Children attending health check | Number of children referred
|  | Total | Boys | Girls | Total
Number of children referred to health clinic for Moderate and Severe Acute Malnutrition (SAM), (disaggregated by gender, % girls) (7) | 5 (40%) | 252 | 3 | 2 | 5
Output Indicator 3.2 | Logframe data | Number of caregivers | Total Trained | Male trained | Female trained | 15 - 24 | 25 - 49 | 50 - 64 | Over 65
Number of caregivers trained in ECD and supporting activities, (disaggregated by gender, % female) (9) | 5 (80%) | 30 | 5 | 1 | 4 | 0 | 5 | 0 | 0
Output Indicator 4.2 | Logframe data | Total Parents | Number positive response
Percentage of parents actively engaged in the activities of the CBCCs (d) | 20% | 50 | 10

## Sheet1 (hidden)
600 |  | 30
60 | 0.1 | 3
120 | 0.2 | 6
180 | 0.3 | 9
240 | 0.4 | 12
300 | 0.5 | 15
360 | 0.6 | 18
420 | 0.7 | 21
480 | 0.8 | 24
540 | 0.9 | 27
600 | 1 | 30
1.1

## TOC Jan 22020 (hidden)
PROJECT TITLE: M'mera Mpoyamba: Investing in effective Early Childhood Development in Blantyre Rural District, Malawi
ASSUMPTIONS
IMPACT |  | NEEDS REVISING?: Enhanced capacity to reduce poverty through provision of improved nutition, health and education to children aged 2-5 in Blantyre district. REWORD: |  |  |  |  | 1. Nutrition, health care and education inputs are sufficient to make significant impact on children's ECD outcomes.
OUTCOME |  | Children aged 2-5 in GVH Malunga, Blantyre District that are holistically developed, i.e. sufficiently and appropriately stimulated, well educated, healthy, well nourished and adequately protected. REWORD: Children aged 2-6 living in 5 catchment areas of GVH Malunga (Blantyre District) are developmentally on track and ready for transition to primary school |  |  |  |  | 2. Nutrition is consistent and measured with regular attendance for improved impact.
3. Content of training suitable for caregivers with a range of formal schooling backgrounds. Caregivers have resources to implement new methods from the training. Caregivers able to adapt generic training to their own CBCC context.
OUTPUTS |  | Creation of safe inclusive and sustainable learning environments at 5 CBCC | Improved health monitoring, hygiene and sanitation in 5 CBCC | Caregivers empowered with knowledge and skills on ECD and able to lead daily activities at 5 CBCC | Increased community engagement, involvement in and ownership of ECD activities | Increased food security and diversification of diet in 5 CBCC | 4. ECD is supported at household level as well as CBCC. Regular attendance at CBCC means child more likely to progress to primary school at age-appropriate time.
5. Climate, water and soil are suitable for the successful production of diversified crops
INPUTS (have added more detail than necessary at the moment to make sure that project activities work with revised TOC. |  | Provision of education resources. Delivery of education activities that are play-based, age appropriate and differentiated for age/ability. | Question - are we doing enough in the project to justify separate outcome? Provision of hygiene packs. WASH training and support to children, caregivers and parents. Health monitoring through mobile health clinic? | Caregiver financial incentive. Training and mentoring for caregivers, covering child development, child protection and inclusion. Improved linkages and referrals? | Parent awareness meetings targeting parents and community members with focus on improving ECD, nutrition, stimulation and school readiness. Parent teacher association. Management committees, | Kitchen gardens: Encouraging growth of medicinal herbs, fresh fruits and vegetables to supplement CBCCs income and improve childrens' diets and nutrition. Training for garden committee. | 6. Other agencies / NGOs or Government authorities do not implement similar or competing activities in the same area without coordination and with contradictory logic of intervention or information
Problem | Under-nutrition and underdevelopment of children aged 2-6 in Blantyre District Malawi
characterised by weak infrastructure, inadequate facilities (unsafe, unhygienic), inadequate trained personnel and ill-trained caregivers, chronic under-funding and low priority with GoM.