## 1. Model budget by year
Format Annual Financial Report Year 2024
Sheet 1 - Budget by year
EXPENSES | Budget 1 January - 31 December | Realisation 1 January - 31 December | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification
I. Direct staff costs applicant
A. Staff costs for non-local personnel of applicant | 992896.7408 | 461619.2152 | 531277.5256 | 42.82%
B. Staff costs for local personnel of applicant | 515271.0453 | 172101.2125 | 343169.8328
C. Programme activity costs, including project management costs | 137166.2986 | 70857.6696 | 66308.629
D. External: consultants and advisers | 0 | 0 | 0
II. Other direct programme costs
A. Activity-related travel costs | 136932.8542 | 77266.9212 | 59665.933 | 41.32% | As the startup of project, the burn rate is currently at 42%, relatively low compared to the elapsed project timeline and budget plan shared earlier. The implementation will be accelerated during the next year as per the budget plan.
B. Project office costs | 208692.8556 | 116609.3274 | 92083.5282
C. Activity-related equipment and investment costs | 66352.7397 | 19942.26 | 46410.4797
D.1 External accountability activities (mid-term review, final evaluation and auditing) | 29166.6667 | 0 | 29166.6667
D.2 Programmatic Monitoring, Evaluation and Learning (executing the learning loop) of the Contributing to Peaceful and Safe Societies 2024-2031 grant programme | 42777.7778 | 8995.07 | 33782.7078
D.3 Costs to participate in the learning trajectory partner | 55278.801 | 0 | 55278.801
III. Subtotal of I and II | 2184535.7795 | 927391.6759 | 1257144.1036
IV. Overheads / indirect costs applicant (fill in your ICR) | 15% | 15% | 0% | 15%
A. (fixed indirect costs rate (=max. 15% of V)) | 327680.3669 | 139108.7514 | 188571.6155 | 42.45%
V. Subtotal Direct costs and indirect costs applicant (=III + IV) | 2512216.1464 | 1066500.4273 | 1445715.7192
VI. Programme costs local partners
A. Direct and indirect costs of local partners (and other third parties) | 0 | 0 | 0 | 0%
VII. Subtotal of V and VI | 2512216.1464 | 1066500.4273 | 1445715.7192
VIII. Contingencies (Max. 4% of VII) | 0% | 0% | 0%
A. Optional amount reserved for contingencies (max 4% of VII) | 0 | 0 | 0 | 0%
IX. Grand total (VII + VIII) | 2512216.1464 | 1066500.4273 | 1445715.7192
INCOME ACTIVITY (source and amount per year)
Dutch Government | 0 | 0 | 0
International Government(s) | 0 | 0 | 0
International Organisation(s) | 0 | 0 | 0
Financial Sector (loan, guarantee, …..) | 0 | 0 | 0
Business contributions | 0 | 0 | 0
Private donors (including private persons) | 0 | 0 | 0
Income generated by the activities (services) funded by MFA | 0 | 0 | 0
Knowledge institutes | 0 | 0 | 0
Other (sources of) income….. | 0 | 0 | 0
Total Income | 0 | 0 | 0

## 2. Model budget by result
Sheet 2 - Budget by result area
| Year 1 |  |  |  |  | Year 2 |  | Year 3
EXPENSES | Budget Result 1 - Evidence-based policy influencing | Realisation Result 1 - Evidence-based policy influencing | Difference 1 June - 31 December | Difference % 1 June - 31 December | Clarification | Budget Result 2 - Country-level adaptive locally led programming | Realisation Result 2 - Country-level adaptive locally led programming | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification | Result 1 - Evidence-based policy influencing | Result 2 - Country-level adaptive locally led programming
I. Direct staff costs applicant | [8 empty] | 244%
A. Staff costs for non-local personnel of applicant | 499446.9492 | 232203.7119 | -267243.2373 | 2.1395 |  | 493449.7915 | 229415.5033 | -264034.2882 |  |  | 50.3% | 49.7%
B. Staff costs for local personnel of applicant | 0 | 0 | 0 |  |  | 515271.0453 | 172101.2125 | -343169.8328 |  |  | 0% | 100%
C. Programme activity costs, including project management costs | 25074.2253 | 12952.8987 | -12121.3266 |  |  | 112092.0733 | 57904.7709 | -54187.3024 |  |  | 18.28% | 81.72%
D. External: consultants and advisers | 0 |  | 0 |  |  |  |  | 0
| Budget Result 1 - Evidence-based policy influencing | Realisation Result 1 - Evidence-based policy influencing | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification | Budget Result 2 - Country-level adaptive locally led programming | Realisation Result 2 - Country-level adaptive locally led programming | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification
II. Other direct programme costs |  |  | 0
A. Activity-related travel costs | 60450.5941 | 34110.3771 | -26340.217 | 1.9402 |  | 76482.2601 | 43156.5441 | -33325.716 | 237.3% |  | 44.15% | 55.85%
B. Project office costs | 35889.4032 | 20053.5814 | -15835.8218 |  |  | 172803.4524 | 96555.746 | -76247.7064 |  |  | 17.2% | 82.8%
C. Activity-related equipment and investment costs | 0 | 0 | 0 |  |  | 66352.7397 | 19942.26 | -46410.4797 |  |  | 0% | 100%
D.1 External accountability activities (mid-term review, final evaluation and auditing | 8750 | 0 | -8750 |  |  | 20416.6667 | 0 | -20416.6667 |  |  | 30% | 70%
D.2 Programmatic Monitoring, Evaluation and Learning (executing the learning loop of the Contributing to Peaceful and Safe Societies 2024-2031 grant programme) | 0 |  | 0 |  |  | 42777.7778 |  | -42777.7778 |  |  | 0% | 100%
D.3 Costs to participate in the learning trajectory partner - highly recommended - see section 12.3 grant policy framework | 55278.801 | 8995.07 | -46283.731 |  |  | 0 | 0 | 0 |  |  | 100% | 0%
0
III. Subtotal of I and II | 684889.9728 | 308315.6391 | -376574.3337 |  |  | 1499645.8067 | 619076.0368 | -880569.7699
| Budget Result 1 - Evidence-based policy influencing | Realisation Result 1 - Evidence-based policy influencing | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification | Budget Result 2 - Country-level adaptive locally led programming | Realisation Result 2 - Country-level adaptive locally led programming | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification
IV. Overheads / indirect costs | 15%
A. (fixed) Indirect costs rate (=max. 15% of V) | 102733.4959 | 46247.3459 | -56486.1501 | 222.1% |  | 224946.871 | 92861.4055 | -132085.4655 | 242.2%
V. Subtotal of III and IV | 787623.4687 | 354562.9849 | -433060.4838 |  |  | 1724592.6777 | 711937.4423 | -1012655.2354
| Budget Result 1 - Evidence-based policy influencing | Realisation Result 1 - Evidence-based policy influencing | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification | Budget Result 2 - Country-level adaptive locally led programming | Realisation Result 2 - Country-level adaptive locally led programming | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification
VI. Programme costs local partners
A. Direct and indirect costs of local partners (and other third parties) | 0 |  | 0 | 0% |  |  |  | -787623.4687 | 0%
VII. Subtotal of V and VI | 787623.4687 | 354562.9849 | -433060.4838 |  |  | 1724592.6777 | 711937.4423 | -1012655.2354
| Budget Result 1 - Evidence-based policy influencing | Realisation Result 1 - Evidence-based policy influencing | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification | Budget Result 2 - Country-level adaptive locally led programming | Realisation Result 2 - Country-level adaptive locally led programming | Difference 1 January - 31 December | Difference % 1 January - 31 December | Clarification
VIII. Contingencies (max. 4% van VII)
A. Optional percentage reserved for contingencies (Max. 4% of VII) | 0 |  | 0 | 0% |  |  |  |  | 0%
VII. Grand total (V + VI) | 787623.4687 | 354562.9849 | -433060.4838 |  |  | 1724592.6777 | 711937.4423 | -1012655.2354
| Year 1 |  |  |  |  | Year 2 |  | Total
2512216.1464

## 3. Model budget by country
Format Annual Financial Report Year 2024 (June to Dec)
Sheet 3 - Indicative budget by country
Please note that this sheet is meant to elaborate the distribution of the costs of result area 2 (country-level adaptive, locally led programming in sheet 2) among the various countries of operation
EXPENSES |  | Budget Country 1 (Sudan) | Realisation Country 1 | Difference 1 June - 31 December | Difference % 1 June - 31 December | Clarification | Budget Country 2 (Iraq) | Realisation Country 2 | Difference 1 June - 31 December | Difference % 1 June - 31 December | Clarification | Budget Country 3 (DRC) | Realisation Country 3 | Difference 1 June - 31 December | Difference % 1 June - 31 December | Clarification | Budget Country 4 (S.Sudan) | Realisation Country 4 | Difference 1 June - 31 December | Difference % 1 January - 31 December | Clarification | Sub Total | Budget Non-country specific expenses | Realisation | Difference 1 June - 31 December | Difference % 1 January - 31 December | Grand Total (=column H + J)
June 1st 2024 to December 2024 |  | 376538.0582 | 294412.267 | -82125.7912 | 78.19% |  | 444119.1222 | 116643.6 | -327475.5222 | 26.26% |  | 408190.9366 | 179086.49 | -229104.4466 | 43.87% |  | 391262.0329 | 65985.07 | -325276.9629 | 16.86% |  | 1312256.5059 | 1086550.4411 | 271264.2489 | -815286.1922 | 24.97% | 2398806.9469
Total per country |  | 376538.0582 | 294412.267 | -82125.7912 | 78.19% |  | 444119.1222 | 116643.6 | -327475.5222 | 26.26% |  | 408190.9366 | 179086.49 | -229104.4466 | 43.87% |  | 391262.0329 | 65985.07 | -325276.9629 | 16.86% |  | 1312256.5059 | 1086550.4411 | 271264.2489 | -815286.1922 | 24.97% | 2398806.9469
Approved budget as per annual plan
Budget |  | Country 1: Sudan | Country 2: South Sudan | Country 3: DRC | Country 4: Iraq | SubTotal | Non-country specific expenses | Grand Total (=column N+P)
First 18 months |  | 968240.7211 | 1006102.3704 | 1049633.8371 | 1142020.6 | 4165997.5286 | 2793986.8484 | 6959984.377
Year 3 |  | 841809.3297 | 357113.5939 | 574816.9185 | 611515.417 | 2385255.2592 | 1684365.973 | 4069621.2322
Year 4 |  | 706980.0216 | 357113.5939 | 500000 | 597544.596 | 2161638.2115 | 1660471.3514 | 3822109.5629
Year 5 |  | 463274.2811 | 428522.6565 | 500000 | 455928.5061 | 1847725.4438 | 1560471.3514 | 3408196.7951
Year 6 |  | 361689.3405 | 426172.0565 | 500000 | 400000 | 1687861.3971 | 1473623.7838 | 3161485.1809
Year 7 |  | 350000 | 400000 | 400000 | 300000 | 1450000 | 1377815.1351 | 2827815.1351
Year 8 |  | 350000 | 400000 | 350000 | 300000 | 1400000 | 1377815.1351 | 2777815.1351
[6 empty] | 0 |  | 0
Total per country |  | 4041993.6941 | 3375024.2713 | 3874450.7556 | 3807009.1191 | 15098477.8402 | 11928549.5782 | 27027027.4183
|  | Year 1 | Year 2 | Year 3 | Year 4 | Total | Total | Total
Forecast June 2024 to Dec 2025 |  | 968240.7211 | 1006102.3704 | 1049633.8371 | 1142020.6 | 4165997.5286 | 2793986.8484 | 6959984.377
Forecast June 2024 to Dec 2024 |  | 376538.0582 | 391262.0329 | 408190.9366 | 444119.1222 | 1620110.15 | 1086550.4411 | 2706660.5911
Sudan
Budget Line | Sum of Amount | Budget Category
A | 97629.1563 | A. Staff costs for non-local personnel of applicant
B | 107237.4625 | B. Staff costs for local personnel of applicant
C | 25831.0596 | C. Programme activity costs, including project management costs
D | 14705.4412 | D. External: consultants and advisers
E | 225.12 | C. Programme activity costs, including project management costs
F | 39195.5874 | B. Project office costs
G | 9588.44 | C. Programme activity costs, including project management costs
Grand Total | 294412.267
Iraq
Budget Line | Sum of Amount | Budget Category
I.A2 | 14500.1 | A. Staff costs for non-local personnel of applicant
I.A3 | 18665.18 | A. Staff costs for non-local personnel of applicant
I.A4 | 15305.18 | A. Staff costs for non-local personnel of applicant
I.A5 | 7200.03 | A. Staff costs for non-local personnel of applicant
I.A6 | 7290.99 | A. Staff costs for non-local personnel of applicant
I.B1 | 4867.47 | B. Staff costs for local personnel of applicant
I.B2 | 5063.83 | B. Staff costs for local personnel of applicant
I.B3 | 7237.98 | B. Staff costs for local personnel of applicant
I.B4 | 11650.4 | B. Staff costs for local personnel of applicant
I.C1 | 904 | C. Programme activity costs, including project management costs
II.A | 10192.9 | A. Activity-related travel costs
II.B | 9133.74 | B. Project office costs
II.C | 4631.8 | C. Activity-related equipment and investment costs
Grand Total | 116643.6
DRC
Budget Line | Sum of Amount | Budget Category
I.A2 | 16956.49 | A. Staff costs for non-local personnel of applicant
I.A3 | 19938.2 | A. Staff costs for non-local personnel of applicant
I.A4 | 26050 | A. Staff costs for non-local personnel of applicant
I.A5 | 3825 | A. Staff costs for non-local personnel of applicant
I.B4 | 8045.37 | B. Staff costs for local personnel of applicant
I.B5 | 2000 | B. Staff costs for local personnel of applicant
I.C1 | 2100 | C. Programme activity costs, including project management costs
II.A1 | 13223.75 | A. Activity-related travel costs
II.A2 | 2244.39 | A. Activity-related travel costs
II.A3 | 18396.13 | A. Activity-related travel costs
II.A4 | 350 | A. Activity-related travel costs
II.A6 | 2002.13 | A. Activity-related travel costs
II.A7 | 3461.5 | A. Activity-related travel costs
II.B1 | 22190 | B. Project office costs
II.B2 | 1055.69 | B. Project office costs
II.B4 | 19117.38 | B. Project office costs
II.B5 | 2820 | B. Project office costs
II.C1 | 115 | C. Activity-related equipment and investment costs
II.C2 | 40 | C. Activity-related equipment and investment costs
II.C3 | 13409 | C. Activity-related equipment and investment costs
II.C4 | 1301.62 | C. Activity-related equipment and investment costs
II.C5 | 444.84 | C. Activity-related equipment and investment costs
Grand Total | 179086.49
South Sudan
Budget Line | Sum of Amount | Budget Category
G.1.1 | 2916.16 | C. Programme activity costs, including project management costs
A.1.1 | 25244.26 | A. Staff costs for non-local personnel of applicant
A.1.2 | 25998.7 | B. Staff costs for local personnel of applicant
H.1.1 | 4000 | C. Programme activity costs, including project management costs
E.1.1 | 5 | B. Project office costs
D.1.1 | 825 | B. Project office costs
F.1.1 | 6995.95 | C. Programme activity costs, including project management costs
Grand Total | 65985.07
Non-country specific expenses
Budget Line | Sum of Amount | Budget Category
I.A. | 143301.86 | A. Staff costs for non-local personnel of applicant
I.C. | 18296.94 | C. Programme activity costs, including project management costs
II.A | 12690.68 | A. Activity-related travel costs
II.B | 22266.93 | B. Project office costs
II.D | 8995.07 | D.1 External accountability activities (mid-term review, final evaluation and auditing)
I.A. | 65712.7689 | A. Staff costs for non-local personnel of applicant
Grand Total | 271264.2489