## All
Updated Monitoring and Evaluation Framework HortiPlus - JAN 2025
FNS Indicators
Result Level | Results chain | Indicator | Unit | Reference value | Cumulative Targets | Target | Target | Target | Target | Sources and means of verification | Collection frequency | Description | Calculation method | Collection manager | Cumulative Targets | Results | Results | Cumulative Results | Rate (%) of | Comments
|  |  |  | 2023 | 2026 | Year 1 | Year 2 | Year 3 | Year 4 | [5 empty] | Y1 + Y2 | Year 1 | Year 2 | Y1 + Y2 | achievement
Description how the activity contributes to the policy theme Food and Nutrition Security | The HortiPlus project aligns with the Food and Nutrition Security policy theme by addressing key objectives such as increasing food availability, improving nutritional quality, and fostering resilience in agricultural systems. The project supports 7,000 smallholder farmers in Burkina Faso by boosting their productivity, income, and climate resilience through sustainable horticultural practices. It enhances dietary diversity for 50,000 rural consumers, increasing access to safe and nutritious foods, which directly contributes to lifting people out of undernourishment. Additionally, HortiPlus fosters private sector development by building the capacities of 100 SMEs and 7 cooperatives, enhancing market access, and facilitating access to finance, which aligns with the Ministry’s goal of creating inclusive, sustainable food systems. By promoting climate-resilient practices and sustainable land use on 800 hectares, the project also supports environmental sustainability. Overall, HortiPlus directly addresses food security, nutrition, and resilience goals, contributing to the Dutch Ministry’s broader agenda for sustainable development and poverty alleviation
Description how the activity contributes to the result are ending hunger and malnutrition | The HortiPlus project contributes to ending hunger and malnutrition in Burkina Faso by focusing on improving food security and nutrition through horticultural development. It aims to increase the production and income of 7,000 smallholder farmers, support 100 SMEs, promote climate resilience, and enhance dietary diversity for 50,000 rural consumers. This is achieved by supporting sustainable farming practices, providing access to quality inputs, promoting nutritious fruits and vegetables, and raising awareness about healthy eating. The HortiPlus project prioritizes nutrient-rich fruits and vegetables to combat vitamin A and iron deficiencies, which lead to health issues like visual impairment and anemia. Selected crops include: - Tomatoes: high in vitamins A and C, and lycopene - Onions: rich in vitamins, minerals, and antioxidants - Cabbage: high in vitamins C and K, and fiber - Amaranth: rich in protein, fiber, and essential micronutrients Through these efforts, HortiPlus helps make nutritious food more available, affordable, and accessible, thereby addressing the root causes of hunger and malnutrition​.
Description how the activity contributes to the result area improving the performance, sustainability and resilience of smallholder farming systems | The HortiPlus project enhances the performance, sustainability, and resilience of smallholder farming systems in Burkina Faso through several targeted interventions. It provides training on Good Agricultural Practices (GAP) and Climate Smart Agriculture (CSA), which help farmers increase productivity while conserving natural resources. By supporting access to quality inputs, financial services, and market linkages, the project strengthens the economic viability of small farms. HortiPlus also promotes the use of organic fertilizers and low-tech innovations like improved irrigation tools to boost yield and reduce environmental impact. Additionally, the project’s focus on resilience-building enables smallholders to better withstand climate change, economic fluctuations, and other external shocks, ensuring long-term sustainability and stability within their farming systems
Overall objective | Improve food and nutrition security in Burkina Faso by:
increasing production (+50%), income (+50%) and climate resilience of 7,000 horticulture farmers,
improving business performance of 7 cooperatives and 100 SMEs
and enhancing diet diversity of 50,000 rural consumers
Outcome 1 | Increased income and production for 7,000 smallholders, and 800 Ha of farmland under sustainable use | 1.1. Number of hectares of farmland under at least 2 conservation practices | ha |  | 800 | 0 | 0 | 200 | 600 | activity report/survey | Year 3 & 4 | measures the number of ha of agricultural land placed under at least 02 conservation practices. | sum | AUXFIN | 0
|  | 1.2. Increased revenues earned by smallholders (F: 40% & <35: 25%) | % |  | 50% | 0 | 0 | 25% | 50% | activity report/survey | Year 3 & 4 | measures the evolution of average annual income from the marketing of horticultural production per hectare and per small producer. it is calculated in years 3 and 4. On the basis of a sample of horticultural producers supported by the project, we calculate the average annual income per hectare of horticultural products and per small producer from which we subtract the average income of the situation of reference, the whole is then divided by the average income at T0 and multiplied by 100 | (current income - T0 income/T0 income)*100 | M&E HortiPlus | 0
|  | 1.3. Number of SSFPs (F: 40%/M:60%) who progressively realize a living income | number of SSFPs | 0 | 5000 (F: 2000- M: 3000) | 0 | 0 | 1000 | 5000 | activity report/survey | Year 3 & 4 | using the living income for rural Burkina Faso as a benchmark, this indicator measures the evolution of average annual income from the marketing of horticultural production per hectare and per small producer. it is calculated in years 3 and 4. On the basis of a sample of horticultural producers supported by the project, we calculate the average annual income per hectare of horticultural products and per small producer from which we subtract the average income of the situation of reference. | sum | M&E HortiPlus | 0
|  | 1.4. Increased volume of fruit and vegetables produced by smallholders (F: 40% & <35: 25%) | % |  | 50% | 0 | 0 | 25% | 50% | activity report/survey | Year 3 & 4 | measures the evolution of the average annual production of horticultural products per hectare and per small producer. it is calculated in years 3 and 4. On the basis of a sample of horticultural producers supported by the project, we calculate the average annual production per hectare of horticultural products and per small producer from which we subtract the production in the reference situation. The whole is then divided by the production T0 and multiplied by 100 | (current production - T0 production/T0 production)*100 | M&E HortiPlus | 0
Outcome 2 | Improved business operations and access to finance and markets of 7 cooperatives and 100 SMEs | 2. Sales increase for SMEs and cooperatives | amount in Euro | 0 | 1300000 | 0 | 0 | 500000 | 1300000 | activity report/survey | Year 3 & 4 | records the amounts of sales of horticultural products made by cooperatives and SMEs supported by HortiPlus | sum | SMEs: M&E HortiPlus Cooperatives: Agriterra | 0
Outcome 3 | 50,000 rural consumers have improved access to safe and nutritious foods. | 3. Number of people with a more diverse and adequate diet (F: 50% & <35: 50%), measured by Household Dietary Diversity (HDDS) | number | 0 | 50000 | 0 | 0 | 0 | 50000 | activity report/ household survey | Year 3, 4 | number of people who consume at least 5 highly nutritious food groups, measured on household level | enumeration | M&E HortiPlus | 0
Outputs | 1.1: AgriCoach app is adapted to local context and selected crops | 1.1.1. Number of crops selected | number | 0 | 6 | 4 | 4 |  |  | study report | Year 1 | lists selected horticultural crops rich in iron and/or vitamin A with high production and commercial potential | enumeration | Sense |  | 6 |  | 6 | 150%
|  | 1.1.2. Number of training videos produced per crop | number | 0 | 15 videos per crop | 0 | 15 videos produced for 3 crops | 15 videos produced for 4 crops | 0 | Video capsules | End Year 2, 3 | counts the video capsules produced in French, Moore and Dioula on good agricultural practices | enumeration | M&E HortiPlus | 15 videos produced for 3 crops | 0 | 114 | 114 | 235%
|  | 1.1.3. Number of crop suitability maps created | number | 0 | 4 | 4 | 0 | 0 | 0 | Activity report | End Year 1 | counts number of crop suitability maps created | enumeration | AUXFIN |  | 12 |  | 12 | 300%
|  | 1.1.4. Climatology and soil data collected and prepared | number | 0 | 1 | 1 | 0 | 0 | 0 | Activity report/ Climate and crop suitability report | End Year 1 | counts number of climatology and soil reports | enumeration | AUXFIN | 1 | 1 |  | 1 | 100%
|  | 1.1.5. Number of G50 groups created | number | 0 | 200 | 60 | 200 | 0 | 0 | UMVA system | End Year 1, 2, 3 | enumeration of G50 registered on the UMVA platform by smallholder farmers producing onions, tomatoes, cabbages, amaranth, peppers and strawberries | enumeration | AUXFIN | 200 |  | 194 | 194 | 97%
| 1.2: Smallholders have capacity to apply GAP and CSA practices on their farms | 1.2.1. Number of activators recruited, trained and supporting G50s | number | 0 | 10 | 5 | 5 | 0 | 0 | Activity report | End Year 1 & 2 | count of all activators recruited and trained to support the HortiPlus G50 | enumeration | AUXFIN | 10 | 7 | 3 | 10 | 100%
|  | 1.2.2. Number of smallholders trained on CSA, GAP and food safety (F: 40% & <35: 25%) | number | 0 | 7000 | 0 | 2000 | 7000 | 7000 | UMVA system | End year 2,3,4 | count of total number of smallholder farmers (members of G50 groups) trained in CSA GAP and food safety through AgriCoach and NutritionCoach | enumeration | AUXFIN | 2000 | 0 | 5920 | 5920 | 296%
|  | 1.2.3. Number of SSFPs applying new technologies/practices that aim to transform food systems towards desirable outcomes (disaggregated for male/female) | number | 0 | 7000 (F: 2800- M: 4200) | 0 | 2000 | 7000 | 7000 | UMVA system | End year 2,3,4 | count of total number of smallholder farmers who acquire information on GAP through the AgriCoach videos(members of G50 groups) | enumeration | AUXFIN | 2000 | 0 | 5920 | 5920 | 296%
|  | 1.2.4. Number of smallholders actively using AgriCoach App (F: 40% & <35: 25%) | number | 0 | 7000 | 0 | 2000 | 7000 | 7000 | UMVA system | End year 2,3,4 | count of total number of smallholder farmers (members of G50 groups) applying AgriCoach skills | enumeration | AUXFIN | 2000 | 0 | N/A | N/A | N/A | This figure will be known after the AgriCoach evaluation that will be conducted in Q1 2025
|  | 1.2.5. Number of smallholders registered on Auxfin UMVA platform (F: 40% & <35: 25%) | number | 0 | 7000 | 2000 | 7000 | 0 | 0 | UMVA system | End year 1, 2, 3, 4 | count of individual smallholder farmers (members of G50 groups) registered on the UMVA platform | enumeration | AUXFIN | 7000 | 0 | 7014 | 7014 | 100%
|  | 1.2.6. Number of hectares of farmland directly reached with activities aimed at structural/systemic improvement of agro-ecological sustainability | ha | 0 | 800 | 0 | 200 | 400 | 800 | activity report/survey | End year 2, 3, 4 | measures the number of ha of agricultural land reached with the application of best practices after AgriCoach training | enumeration | AUXFIN | 200 | 0 | 0 | 0 | 0% | This figure will be known after the AgriCoach evaluation that will be conducted in Q1 2025
| 1.3: Smallholder farmers have access to financial services | 1.3.1. Number of MFIs connected to UMVA system | number | 0 | 2 | 1 | 2 | 0 | 0 | UMVA system | End year 1, 2, 3, 4 | enumeration of MFIs connected to the UMVA system | enumeration | AUXFIN | 2 | 2 | 0 | 2 | 100%
|  | 1.3.2. Number of smallholders actively accessing credit through UMVA system (F: 40% & <35: 25%) | number | 0 | 4000 | 0 | 1800 | 4000 | 4000 | UMVA system | End year 2,3,4 | enumeration of smallholder farmers accessing credit trhough UMVA system | enumeration | AUXFIN | 1800 | 0 | 0 | 0 | 0% | This activity has been delayed because of more stringent account registration. A strategy is in place to catch up on these targets in 2025 conditions
|  | 1.3.3. % of credits paid back | % | 0 | 95% | 0% | 95% | 95% | 95% | UMVA system | End year 3, 4 | proportion of credits repaid out of all credits granted | (credits repaid - credits granted/credits granted)*100 | AUXFIN | 95% | 0 | 0 | 0 | 0% | No credits have yet been enabled. See comment above.
|  | 1.3.4. Number of smallholders trained through FinanceCoach app (F: 40% & <35: 25%) | number | 0 | 7000 | 0 | 2000 | 7000 | 7000 | UMVA system | End year 2,3,4 | enumeration of small farmers trained in the use of FinanceCoach disaggregated by women and young people | enumeration | AUXFIN | 2000 | 0 | 0 | 0 | 0% | Because of the delay in the acces-to-credit activity, FinanceCoach training is delayed as well. A strategy is in place to catch up on these targets in 2025.
| 1.4: Smallholders have access to quality horticulture input packages developed and low-tech innovations | 1.4.1. Number of input packages developed | number | 0 | 4 | 0 | 6 | 6 | 6 | Activity report | End Year 2 & 3 | enumeration of input packages specific to the production of tomatoes, onions, cabbage and amaranth |  | Sense | 6 | 6 | 0 | 6 | 150%
|  | 1.4.2. % of smallholders accessing input packages (F: 40% & <35: 25%) | % | 0 | 75% | 0% | 0% | 25% | 75% | UMVA system | End Year 2, 3, 4 | calculation of the proportion of the number of tomato, onion, cabbage, amaranth producers benefiting from HortiPlus who use the input packages developed in relation to all producers benefiting from HortiPlus | (producers of tomatoes, onions, cabbage, amaranth beneficiaries of HortiPlus who use the input packages developed/total number of producers beneficiaries of HortiPlus) * 100 | M&E HortiPlus | 0%
|  | 1.4.3. Total number of demonstration plots of low-tech innovations established | number | 0 | 21 | 0 | 12 | 31 | 21 | Activity report | End Year 2, 3, 4 | enumeration of demonstration plots of low-tech innovations set up by HortiPlus | enumeration | M&E HortiPlus | 12 | 0 | 44 | 44 | 376%
|  | 1.4.4. % of farmers applying new low-tech solutions on their plots (F: 40% & <35: 25%) | % | 0 | 50% | 0% | 0% | 50% | 50% | Project administration: activator survey | End Year 3, 4 | proportion of smallholder farmers beneficiaries of HortiPlus applying new low-tech solutions on their plots in relation to all producers benefitting from HortiPlus | (producers beneficiaries of HortiPlus who apply new low-tech solutions to their plots/total number of producers beneficiaries of HortiPlus) * 100 | M&E HortiPlus | 0%
| 1.5: NutritionCoach is adapted to local context and used by smallholders and their families | 1.5.1.Number of smallholders trained on nutrition | number | 0 | 7000 | 0 | 0 | 2000 | 7000 | UMVA system | End Year 3, 4 | count of smallholders who acquire information on dietary diversity thanks to Nutrition Coach | enumeration | AUXFIN | 0
|  | 1.5.2. Number of people directly reached with activities aimed at structural/systemic improvement of their nutritional situation | number | 0 | 7000 | 0 | 0 | 2000 | 7000 | UMVA system | End Year 3,4 | count of smallholders who acquire information on dietary diversity thanks to Nutrition Coach | enumeration | AUXFIN | 0
|  | 1.5.3. Number of people indirectly reached aimed at structural/systemic improvement of their nutritional situation | number | 0 | 43000 | 0 | 0 | 12500 | 30500 | AUXFIN: Jeanne app | End Year 3,4 | count of households members of smallholder farmers beneficiaries of HortiPlus who have been indirectly reached by the information deployed through Nutrition Coach | enumeration | AUXFIN | 0
| 1.6: Social media campaigns on dietary diversity developed and rolled-out | 1.6.1. Reach of Facebook campaign (F: 50% & <35: 50%) | follower | 0 | 10000 | 0 | 2000 | 5000 | 10000 | Facebook analytics | End Year 2, 3, 4 | counting followers of posts on HortiPlus social media pages | social media analysis | M&E HortiPlus | 2000 | 0 | 2550 | 2550 | 128% | These are the number of followers on our Facebook page. Overall, the posts generated 335,000 views in 2024.
|  | 1.6.2. Number of total posts (video, events, photos) | publication | 0 | 150 | 0 | 50 | 100 | 150 | Facebook analytics | End Year 2, 3, 4 | counting text, photo, video and photo posts on HortiPlus social media pages | social media analysis | M&E HortiPlus | 50 | 0 | 232 | 232 | 464%
| 2.1: 100 SMEs received business support and matchmaking | 2.1.1. Number of factsheets with latest insights on business opportunities and value chain developments on four crops developed | number | 0 | 4 | 0 | 1 | 1 | 2 | Factsheets | End Year 2, 3, 4 | count of factsheets presenting the latest information on commercial opportunities and the evolution of the value chain of the speculations developed | enumeration | M&E HortiPlus | 1 | 0 | 2 | 2 | 200%
|  | 2.1.2. Number of SMEs participating in and benefitting from Business training | number | 0 | 40 | 20 | 20 | 0 | 0 | Project administration: participants list and satisfaction survey | End Year 1, 2 | count of SMEs having participated in Business Training | enumeration | M&E HortiPlus | 40 | 17 | 30 | 47 | 118%
|  | 2.1.3. Number of SMEs participating in and benefitting from Masterclasses | number | 0 | 80 | 0 | 30 | 30 | 20 | Project administration: participants list and satisfaction survey | End Year 2, 3, 4 | count of SMEs having participated in Masterclasses | enumeration | M&E HortiPlus | 30 | 0 | 69 | 69 | 230%
|  | 2.1.4. Number of sales contracts for SMEs | number | 0 | 10 | 0 | 5 | 5 | 0 | SMEs: financial administration | Year 2, 3, 4 | count of sales contracts signed by SMEs between 2023 and 2026 | enumeration | M&E HortiPlus | 5 | 0 | 0 | 0 | 0% | A strategy is in place to catch up on this target in 2025
|  | 2.1.5. Sales increase created for SMEs and cooperatives | euro | 0 | 1300000 | 0 | 0 | 500000 | 800000 | reports, assessments | Year 3, 4 | cumulative sum of turnover from the sale of horticultural products by SMEs and cooperatives | sum of turnover of SMEs and cooperatives | M&E HortiPlus | 0
| 2.2: Finance is raised for horticulture SMEs | 2.2.1. Number of SMEs that obtained growth finance | number | 0 | 5 | 0 | 2 | 2 | 2 | SMEs: loan agreement | Year 2, 3, 4 | counting of bank loan contracts contracted by SMEs | enumeration | M&E HortiPlus | 2 | 0 | 0 | 0 | 0% | A strategy is in place to catch up on this target in 2025
|  | 2.2.2. Value of working capital and project finance obtained for SMEs in EUR | euro | 0 | 500000 | 0 | 100000 | 200000 | 200000 | SMEs: loan agreement | Year 2, 3, 4 | Cumulative sum of loan amounts granted to SMEs by banks | enumeration | M&E HortiPlus | 100000 | 0 | 0 | 0 | 0% | A strategy is in place to catch up on this target in 2025
| 2.3: New products, services and business models introduced via Innovation Fund | 2.3.1. Number of proposals received | number | 0 | 50 | 0 | 50 | 0 | 0 | Activity report | Year 2 | count of funding requests received | enumeration | M&E HortiPlus | 50 | 0 | 273 | 273 | 546%
|  | 2.3.2. Number of proposals awarded | number | 0 | 3 | 0 | 3 | 0 | 0 | Activity report | Year 2 | count of funding requests granted | enumeration | M&E HortiPlus | 3 | 0 | 3 | 3 | 100%
|  | 2.3.3. Total amount in Euro of the innovation fund granted to SMEs | euro | 0 | 120000 | 0 | 120000 | 0 | 0 | activity report/grant contracts | Year 2 | sum of amounts allocated to innovation fund winners | sum | M&E HortiPlus | 120000 | 0 | 120000 | 120000 | 100%
|  | 2.3.4. Number of new products, services and business models introduced to the horticulture sector | number | 0 | 3 | 0 | 0 | 2 | 1 | Activity report | Year 3, 4 | count of new products/services/business models introduced in the horticultural sector created thanks to innovation funds | enumeration | M&E HortiPlus | 0
|  | 2.3.5. Sales increase created for SMEs in Euros | euro | 0 | 300000 | 0 | 0 | 100000 | 200000 | end-report from beneficiery SMEs of Innovation Fund | Year 3, 4 | cumulative sum of turnover from the sale of innovations by SMEs | sum | M&E HortiPlus | 0
|  | 2.3.6. Number of smallholder farmers acquired new market, services and/or products (F: 25% & <35: 25%) | number | 0 | 200 | 0 | 0 | 70 | 200 | Project administration: end-report from beneficiery SMEs of Innovation Fund | Year 3, 4 | count of small farmers who have acquired new markets, services and/or products thanks to innovation funds | enumeration | M&E HortiPlus | 0
| 2.4: Bio-PGS certification rolled-out, including additional smallholders, SMEs and sales outlets | 2.4.1. Number of SMEs and farmer groups that receive training on Bio-PGS certification | number | 0 | 3 SMEs | 0 | 3 SMEs | 3 SMEs | 0 | Activity report | Year 3 | Count of SMEs and farmer groups that have been trained in Bio-PGS certification | enumeration | M&E HortiPlus | 3 SMEs | 0 | 0 | 0 | 0% | The SME selection has taken place and they will receive training in Q2 2025
[5 empty] | 6 farmer groups | 0 | 6 farmer groups | 6 farmer groups | 0 | [5 empty] | 6 farmer groups | 0 | 0 | 0 | 0% | The farmer groups have been selected and received training in Q1 2025.
|  | 2.4.2. Number of SMEs and farmer groups with Bio-PGS certification | number | 0 | 3 SMEs | 0 | 0 | 0 | 3 SMEs | list of Bio SPG certified SMEs and farmer groups published by CNA Bio | Year 4 | count of SMEs and farmer groups that have obtained Bio SPG certification | enumeration | M&E HortiPlus | 0
[5 empty] | 6 farmer groups | 0 | 0 | 0 | 6 farmer groups | [5 empty] | 0
|  | 2.4.3. Number of new outlets that sell Bio-PGS certified fruits & vegetables | number | 0 | 10 | 0 | 0 | 0 | 10 | Activity report | Year 4 | count of new points of sale for Bio SPG products created | enumeration | M&E HortiPlus | 0
|  | 2.4.4. Number of smallholder farmers with new markets (F: 25% & <35: 25%) | number | 0 | 150 | 0 | 0 | 0 | 150 | Activity report | Year 4 | count of small farmers who have acquired new markets, thanks to Bio SPG certification | enumeration | M&E HortiPlus | 0
| 2.5: Cooperatives with strengthened business operations | 2.5.1. Number of cooperatives that improved their operations and structures | number | 0 | 7 | 0 | 7 | 0 | 0 | Activity report | Year 2, 3 | Count of cooperatives that have implemented action plans developed during HortiPlus | enumeration | Agriterra | 7 | 7 | 7 | 7 | 100%
|  | 2.5.2. Number of cooperatives trained in business development | number | 0 | 7 | 0 | 7 | 0 | 0 | Activity report | Year 2, 3 | Count of cooperatives that have been trained in business development | enumeration | Agriterra | 7 | 7 | 7 | 7 | 100%